**Village of Bennington Water Distribution Extensions**

**Weekly Update**

**Work Completed - Week of November 20, 2017 through December 1, 2017**

**Murphy Road/River Road/Ore Bed Road/River Road**

* Started with service piping to buildings.

**Riverside Drive**

* Continued directional drilling 6-inch HDPE water main under stream ongoing.

**Park Street**

* Finished installing main line

**Matt Drive**

* Finished installing water main.

**Total Water Main Installed since November 17, 2017**

* 2,809 ft of water main installed.

**Water Main Installed To Date and % of Total Project**

* 8,704 ft of water main installed (36% of total water main for the project)

**Issues Encountered/Notices**

* Roads where mains are being installed will be closed to thru traffic, but will remain open to local residents, school buses and emergency vehicles.
* OCE will continue to coordinate with residents regarding service line construction/easements.

**Work Anticipated for Week of December 4, 2017 through December 8, 2017**

* Water service crew will continue installing service pipe on Murphy Road/Matteson/ River Road/Ore Bed Road/River Road/Matt Drive. Interior connection will be made next year.
* Continue directional drill on Riverside Drive, Park Street and Ore Bed Road.
* Water main crew will continue to installing water main pipe on Riverside.