**Village of Bennington Water Distribution Extensions**

**Weekly Update**

**Work Completed - Week of December 4, 2017 through December 8, 2017**

**Murphy Road/ River Road/ Harrington Road**

* Continued with service piping to buildings.

**Riverside Drive**

* Continued directional drilling 6-inch HDPE water main under stream.

**Park Street**

* Continued water main construction.

**Matt Drive and Matteson Road**

* Water main hydrostatic and leakage testing.

**Total Water Main Installed this week**

* 2,076 ft of water main installed.

**Water Main Installed To Date and % of Total Project**

* 10,780 ft of water main installed (50% of total water main for the project)

**Issues Encountered/Notices**

* Roads where mains are being installed will be closed to thru traffic, but will remain open to local residents, school buses and emergency vehicles.
* OCE will continue to coordinate with residents regarding service line construction/easements.

**Work Anticipated for Week of December 11, 2017 through December 15, 2017**

* Water service crew will continue installing service pipe on Murphy Road/Harrington. *Interior connection will be made next year.*
* Continue directional drill on Riverside Drive, Park Street and Ore Bed Road.
* Water main crew will begin installing water main pipe on Riverside.