## Guide
Guide to Using the Performance Standards
Introduction
The Ecosystem Restoration Program (ERP) Performance Standards serve as a guide for applicants and Grantees in developing high quality and successful projects. The Performance Standards are meant to help potential grantees:
▪ categorize the project types that are described in their proposal
▪ choose milestones and deliverables that are appropriate for their proposal
▪ understand the project types and criteria for funding of ERP
▪ understand the performance data reporting requirements of ERP
ERP requires that applicants include at least one performance measure and a table of milestones and deliverables in their proposal. An example table are is included on the "Example Milestones Table" tab.
Using the Standards
The Performance Standards are organized into five columns: Project Type, Criteria for Funding, Milestones, Deliverables, and Performance Reporting. Each of these are detailed below. Please note that most projects will not include all of the elements from each cell, all the milestones or deliverables may not be relavant, these are provided as suggestions. The applicant should use this to choose the appropriate components from the table and the Performance Reporting tool for their specific projects.
Project Type:
The Project Type column is the starting point for using the Standards. These projects types cover the vast majority of projects that ERP funds, however not all projects funded by ERP will fit into one of these categories and many often span more than one type. Read across the colored row that corresponds the project type or types.
Criteria for Funding:
This cell outlines some of the criteria that are used to determine if the project is eligible for funding through ERP. There are many factors in determining eligibility, they are outlined in the Request for Proposals (RFP), however this documents some of the specific criteria that are importance to consider for a given project type.
Example milestones:
This cell lists potential activities that may serve of indicators of progress
Deliverables:
This cell outlines lists potential deliverables to be produced as the project proceeds. The payment schedule will be structured around this list.
Performance reporting:
The tool on this tab will generate a list of specific data for each project type that are required and highly recommended to be reported in a final project report. These data will be incorporated into an annual analysis and report of ERP-funded projects to track program success.
Example Milestones Table
This table show a example of how the Standards come together to create a Milestones table for aproject.

## Performance Standards
Project Type | Criteria for Funding | Example Milestones | Example Deliverables | Performance Reporting
Project Development | Approved selection and prioritization methodology ANR technical staff concurrence | Site locations and boundaries identified Ownership identified Restoration needs identified Restoration objectives identified Prioritization criteria developed Project prioritization completed Priority sites secured for implementation | Locator map Prioritized project list Project summaries Site photos (minimum resolution of 1200 x 1600) Prioritization criteria Performance report | See Performance Reporting Tab for Required & Recommended Data Reporting
Riparian Planting (simple) | Average buffer width of 35' (no less than 25' in any location) Average buffer width of 25' allowed in developed )(non-agricultural and forested) landscapes if constrained by existing buildings and other developments Minimum planting density of 300 plants per acre Native species For 35' buffer no more than $4,500 per acre For 25' buffer no more than $2,500 per acre ANR technical staff concurrence ERP funding not being used as an alternative to CREP Minimum of a 10 year landowner and stewardship agreement | Sites identified Constraints identified Planting plan developed Landowner and stewardship agreement signed Supplies and materials ordered Planting completed | Locator map Planting plan (including species type, number, and estimated cost) Signed landowner and stewardship agreement (including timing and completion of plant protection removal) Before, during, and after photos (minimum resolution of 1200 x 1600) Project summary Performance report | See Performance Reporting Tab for Required & Recommended Data Reporting
Riparian Restoration (complex) | Average buffer width of 35' (no less than 25' in any location) Average buffer width of 25' allowed in developed )(non-agricultural and forested) landscapes if constrained by existing buildings and other developments Minimum planting density of 300 plants per acre Native species For 35' buffer no more than $4,500 per acre For 25' buffer no more than $2,500 per acre ANR technical staff concurrence ERP funding not being used as an alternative to CREP Minimum of a 10 year landowner and stewardship agreement | Sites identified Constraints identified Planting plan developed Landowner and stewardship agreement signed Supplies and materials ordered Restoration completed | Locator map Planting plan (including species type, number, and estimated cost) Signed landowner and stewardship agreement Before, during, and after photos (minimum resolution of 1200 x 1600) Project summary Performance report | See Performance Reporting Tab for Required & Recommended Data Reporting
Stormwater - Residential | Acceptable sizing and design criteria Not required by a federal or state permit Eligible BMPs 75% of funding used for BMP installation ANR technical staff concurrence Minimum of a 10 year landowner and stewardship agreement | Sites identified Site assessments completed Constraints identified Remediation plan developed Signed landowner and stewardship agreement Best management practices installed | Locator map Site sketch Signed landowner and stewardship agreement Before and after photos (minimum resolution of 1200 x 1600) Performance report | See Performance Reporting Tab for Required & Recommended Data Reporting
Stormwater - Design | Eligible quotes/bids Not required by a federal or state permit ANR technical staff concurrence Landowner commitment | Request for proposals developed Contractor selected Kick-off meeting held Existing conditions documented Alternatives evaluated Alternative selected Hydrologic and hydraulic analysis completed 30% design completed Comments and responses documented Regulatory requirements documented 100% design completed Cost estimates prepared Contract bidding documents prepared | Locator map Signed landowner commitment Alternatives Analysis (see ERP Project Design Terminology and Guidance) 30%/90%/100% Design (see ERP Project Design Terminology and Guidance) Comments and responses Site photos (minimum resolution of 1200 x 1600) Project summary Performance report | See Performance Reporting Tab for Required & Recommended Data Reporting
Stormwater - Construction | Eligible quotes/bids Not required by a federal or state permit Permits secured ANR technical staff concurrence Minimum of a 10 year landowner and stewardship agreement | Request for proposals developed Contractor selected Kick-off meeting held Practice installed Operations and maintenance plan developed Maintenance agreement signed | Locator map Construction (see ERP Project Design Terminology and Guidance) Permits Annotated/as-built plans Signed landowner agreement Stewardship/maintenance plan Before, during, and after photos (minimum resolution of 1200 x 1600) Project summary Performance report | See Performance Reporting Tab for Required & Recommended Data Reporting
Stormwater Master Planning | Recommended as a strategy in basin plan or other regional planning document High priority area | Existing data, program analysis & associated documents collected Data gaps documented Field survey completed Meetings with town staff, selectboard Draft plan developed Final plan developed | Stormwater library Problem area list with maps prioritized on feasibility, funding and implementation logistics Final plan | See Performance Reporting Tab for Required & Recommended Data Reporting
Backroad Erosion Control | High priority road segment or exigent site Minimum of a 10 year landowner and stewardship agreement | Sites identified Contractor selected Designs developed Materials and supplies ordered Best management practices implemented | Locator map Sketch plan Signed landowner and stewardship agreement Before and after photos (minimum resolution of 1200 x 1600) Project summary Performance report | See Performance Reporting Tab for Required & Recommended Data Reporting
Agricultural Pollution Prevention | High priority or critical source area Other funding insufficient or not eligible Minimum of a 10 year landowner and stewardship agreement | Sites identified Contractor selected Designs developed Materials and supplies ordered Best management practices implemented Landowner agreement signed | Locator map Practice details Signed landowner and stewardship agreement Before and after photos (minimum resolution of 1200 x 1600) Project summary Performance report | See Performance Reporting Tab for Required & Recommended Data Reporting
River Corridor Easement | High priority area ANR technical staff concurrence | Conservation documents drafted Property survey completed Title search completed Baseline documentation reported Closing scheduled Purchase and sale agreement signed Long term monitoring plan developed | Draft easement Survey Title opinion Baseline documentation report Purchase and sale agreement Long-term monitoring plan Performance report | See Performance Reporting Tab for Required & Recommended Data Reporting
SGA Phase 1 | High priority area Receptive community | Baseline data created including reach breaks, mcl, and valley wall SGAT run Data entered into DMS QA complete Report complete | SGAT project on CD Verified data entry QA documentation 3 paper copies and 1 digital copy or report | See Performance Reporting Tab for Required & Recommended Data Reporting
SGA Phase 2 | High priority area Receptive community | Reaches selected and landowner permission obtained Field work complete Data entered into DMS QA complete Report complete | Verified data entry in DMS for steps 1 and 2 Updated SGAT project including field verified valley walls and segmentation breaks QA documentation 3 paper copies and 1 digital copy of report | See Performance Reporting Tab for Required & Recommended Data Reporting
Corridor Planning | High priority area Receptive community | Steering committee established Scoping meeting held Corridor Plan drafted 5 project packets developed Corridor Plan finalized Results presented | Minutes from steering committee meetings Digital copy of draft Corridor Plan Project packets including notes from landowner meetings 3 paper copies and 1 digital copy of final Corridor Plan Minutes from public meetings | See Performance Reporting Tab for Required & Recommended Data Reporting
Floodplain/Stream Restoration | High priority area ANR technical staff concurrence | Site/s identified Request for proposals developed Consultant selected Baseline SGA and hydrology/hydraulics developed (as appropriate) 75% designs completed 100% designs Completed Contractor selected Kick-off meeting held Project completed | Locator map Site Plan inclusive of topographic and boundary survey Signed Landowner Agreement/s Final Designs/Plans (for rivers include SGA and hydrologic and hydraulic analyses) Project Summary Before/After photos (min resolution of 1200 x 1600) Performance Report As-built plans (for rivers include cross-sections) Monitoring plan (include removal of plant protection if applicable) | See Performance Reporting Tab for Required & Recommended Data Reporting

## Performance Reporting
WHAT DATA DO I NEED TO REPORT?
Insructions for using this reference table:
To find out what particular performance measures are required (primary performance measures) and highly recommended (additional reporting data) on your particular project, click on the bright yellow worksheet cell and use the arrow that appears to select your project type. The data to be reported will automatically change according to the project type selected. We recommend that these data are clearly reported in a table within a project report.
Please note that projects that encompass more than one project type will need to report more than one set of reporting data.
Select project type here → | Agricultural Pollution Prevention
Primary performance measures: | #, type and size of practices
# of acres improved
Additional reporting data: | Practice standard used
# of sites
Estimate of environmental improvement
Quantity
Quality
Cost per acre improved/treated
Why are we being asked to report these specific things?
With passage of Act 168 the ERP grants program, like any entity that manages state resources, is required to evaluate and report how monies spent are affecting change "on the ground." One of the best ways to do this is to collect consistent data by project types. While these data cannot capture all the value within a particular project, it will allow us to answer the question, "What are we getting for our money?"

## Example Milestones Table
The following table shows how the performance standards for a riparian planting project may be structured in a proposal. This structure allows a grantee to invoice by milestone using the performance measure as a base. As each acre was identified a grantee could submit an invoice for each milestone based on the acreage of the site.
Project type: Riparian planting
Performance Measure: # of acres of streambank planted |  | 5 acres planted
Milestone |  | Deliverables | Cost/Unit | Payment
1 | Identify sites Identify constraints | Locator map Site descriptions | $450/acre | No to exceed $2,250
2 | Develop planting plan Secure landowner agreement Develop sterwadship plan | Planting plan (including species type, number, and estimated cost) Signed landowner agreement Stewardship plan | $900/acre | Not to exceed $4,500
3 | Order supplies and materials | Supply and material invoices | $2,700/acre | Not to exceed $13,500
4 | Complete planting | Before, during, and after photos (minimum resolution of 1200 x 1600) Project summary Performance report | $450/acre planted | Not to exceed $2,250
| TOTAL |  |  | 22500
Performance Reporting Data
# acres streambank planted # of feet of streambank planted # of sites # of plantings Density of plantings Plant protection used (yes,no) Total cost per acre

## Sheet1_ (hidden)
Project Category | PM 1 | PM 2 | PM 3 | PM 4 | PRD 1 | PRD 2 | PRD 3 | PRD 4 | PRD 5 | PRD 6 | PRD 7
Agricultural Pollution Prevention | #, type and size of practices | # of acres improved |  |  | Practice standard used | # of sites | Estimate of environmental improvement | Quantity | Quality | Cost per acre improved/treated
Backroad Erosion Control | # and type of practices | # of feet of drainage improved |  |  | Design standard used | # of sites | Estimate of environmental improvement | Quantity | Quality | Cost per linear foot improved
Corridor Planning | PM 1: # of projects identified; PRD 1: # of projects ready to be implemented; PRD 2: Total cost per stream mile
Floodplain/Stream Restoration | # of floodplain encroachments removed | # of acres of reconnected floodplain | # of acres of wetland restored | # of acres of streambank planted | # of lineal feet of stream channel reconnected to floodplain | # of feet of streambank planted | # of sites | # of plants | Density of plants | Plant protection used (yes,no)
Project Development | PM 1: # and type of priority projects identified; PM 2: # of projects prioritized; PRD 1: % of sites secured
Riparian Planting (simple) | # of acres of streambank planted |  |  |  | # of feet of streambank planted | # of sites | # of plants | Density of plants | Plant protection used (yes,no) | Total cost per acre
Riparian Restoration (complex) | # of acres of streambank restored |  |  |  | # of feet of streambank planted | # of sites | # of plants | Density of plants | Plant protection used (yes,no) | Total cost per acre | Method of stabilization
River Corridor Easement | PM 1: # of acres of corridor conserved; PRD 1: # of feet of corridor conserved; PRD 2: Total cost per acre
SGA Phase 1 | PM 1: # of stream miles assessed; PRD 1: Total cost per stream mile
SGA Phase 2 | PM 1: # of stream miles assessed; PRD 1: Total cost per stream mile
Stormwater - Construction | # and types of practices installed | # of acres of impervious treated | # of gallons of stormwater treated or retained |  | Design standard used | Dimensions of practice | Quantitative estimate of environmental improvement | Qualitative estimate of environmental improvement | Water quality volume | Cost per impervious acre/cubic foot treated
Stormwater - Design | PM 1: # and level of designs completed; PRD 1: Design standard used; PRD 2: Type of practice; PRD 3: Cost; PRD 4: Quantitative estimate of environmental improvement; PRD 5: Qualitative estimate of environmental improvement
Stormwater - Residential | # of acres of impervious area treated | # of gallons of stormwater treated or retained |  |  | # of sites | # and type of best management practices installed | Sizing and design criteria used | Cost per acre treated | Cost per gallon treated/retained
Stormwater Master Planning | PM 1: # of acres covered by plan; PRD 1: # of projects scheduled for implementation; PRD 2: Improvement in water quality and/or reduction in public complaints

## Sheet1 (hidden)
Project Category | PM 1 | PM 2 | PM 3 | PM 4 | PRD 1 | PRD 2 | PRD 3 | PRD 4 | PRD 5 | PRD 6 | PRD 7
Agricultural Pollution Prevention | #, type and size of practices | # of acres improved |  |  | Practice standard used | # of sites | Estimate of environmental improvement | Quantity | Quality | Cost per acre improved/treated
Backroad Erosion Control | # and type of practices | # of feet of drainage improved |  |  | Design standard used | # of sites | Estimate of environmental improvement | Quantity | Quality | Cost per linear foot improved
Corridor Planning | PM 1: # of projects identified; PRD 1: # of projects ready to be implemented; PRD 2: Total cost per stream mile
Floodplain/Stream Restoration | # of floodplain encroachments removed | # of acres of reconnected floodplain | # of acres of wetland restored | # of acres of streambank planted | # of lineal feet of stream channel reconnected to floodplain | # of feet of streambank planted | # of sites | # of plants | Density of plants | Plant protection used (yes,no)
Project Development | PM 1: # and type of priority projects identified; PM 2: # of projects prioritized; PRD 1: % of sites secured
Riparian Planting (simple) | # of acres of streambank planted |  |  |  | # of feet of streambank planted | # of sites | # of plants | Density of plants | Plant protection used (yes,no) | Total cost per acre
Riparian Restoration (complex) | # of acres of streambank restored |  |  |  | # of feet of streambank planted | # of sites | # of plants | Density of plants | Plant protection used (yes,no) | Total cost per acre | Method of stabilization
River Corridor Easement | PM 1: # of acres of corridor conserved; PRD 1: # of feet of corridor conserved; PRD 2: Total cost per acre
SGA Phase 1 | PM 1: # of stream miles assessed; PRD 1: Total cost per stream mile
SGA Phase 2 | PM 1: # of stream miles assessed; PRD 1: Total cost per stream mile
Stormwater - Construction | # and types of practices installed | # of acres of impervious treated | # of gallons of stormwater treated or retained |  | Design standard used | Dimensions of practice | Quantitative estimate of environmental improvement | Qualitative estimate of environmental improvement | Water quality volume | Cost per impervious acre/cubic foot treated
Stormwater - Design | PM 1: # and level of designs completed; PRD 1: Design standard used; PRD 2: Type of practice; PRD 3: Cost; PRD 4: Quantitative estimate of environmental improvement; PRD 5: Qualitative estimate of environmental improvement
Stormwater - Residential | # of acres of impervious area treated | # of gallons of stormwater treated or retained |  |  | # of sites | # and type of best management practices installed | Sizing and design criteria used | Cost per acre treated | Cost per gallon treated/retained
Stormwater Master Planning | PM 1: # of acres covered by plan; PRD 1: # of projects scheduled for implementation; PRD 2: Improvement in water quality and/or reduction in public complaints