**Village of Bennington Water Distribution Extensions**

**Weekly Update**

**Work Completed - Week of November 6, 2017 through November 11, 2017**

**Murphy Road**

* Installed services for one day. Installed were three corporation stops and one curb stop.

**Ore Bed Road**

* Directional drill began under the brook. Driller is having a hard time due to encountering cobles/rocks or ledge.
* Trench preparation for paving.

**Harrington Road**

* Installed main line.

**Park Street**

* Drilling and blasting was conducted throughout the week.

**Total Water Main Installed this Week**

* 1,316 ft

**Water Main Installed To Date and % of Total Project**

* 4,909 ft of water main installed (23% of total water main for the project)

**Issues Encountered/Notices**

* Roads where mains are being installed will be closed to thru traffic, but will remain open to local residents, school buses and emergency vehicles.
* OCE will coordinate with residents regarding service line construction. Services will be brought into the homes but not connected. Connections will be made next year.

**Work Anticipated for Week of November 13, 2017 through November 18, 2017**

* Water main crew will finish installing pipe on Harrington Road and River Road.
* Water main crew will begin installing pipe on Park Street.
* Water service line installation may continue on Murphy and Ore Bed Road.
* Directional Drill may begin on Riverside.
* Fix water leak on existing water main on Murphy Road.
* Install trench patch pavement on Murphy Road and Ore Bed Road.