**Village of Bennington Water Distribution Extensions**

**Weekly Update**

**Work Completed - Week of November 13, 2017 through November 17, 2017**

**Murphy Road**

* Completed paving of all trench patch.

**Ore Bed Road**

* Completed paving of all trench patch.

**Harrington Road**

* Completed paving of all trench patch.

**Riverside Drive**

* Directional drilling 6-inch HDPE water main under stream.

**Park Street**

* Installing main line

**Matt Drive**

* Mobilized and begin to install main line.

**Total Water Main Installed this Week**

* 987 ft of water main installed.

**Water Main Installed To Date and % of Total Project**

* 5,895 ft of water main installed (27% of total water main for the project)

**Issues Encountered/Notices**

* Roads where mains are being installed will be closed to thru traffic, but will remain open to local residents, school buses and emergency vehicles.
* OCE will coordinate with residents regarding service line construction.

**Work Anticipated for Week of November 18, 2017 through November 22, 2017**

* Water main crew will continue to installing pipe on Park Street and Matt Drive.
* Continue directional drill on Riverside
* Begin blasting of ledge/rock on Riverside (Old Stagecoach Road).
* Water service line installation may continue on Murphy. Services will be brought into the homes but not connected. Connection will be made next year.