**Village of Bennington Water Distribution Extensions**

**Weekly Update**

**Work Completed - Week of December 11, 2017 through December 15, 2017**

**Murphy Road/Harrington Road**

* Continued with service piping to buildings.

**Riverside Drive**

* Continued with drilling and blasting
* Resumed with directional drilling 6-inch HDPE water main under stream.
* Continued with water main construction.

**Park Street**

* Completed water main construction.

**Matt Drive and Matteson Road**

* Water main hydrostatic and leakage testing.

**Total Water Main Installed this week**

* 1,236’ ft of water main installed.

**Water Main Installed To Date and % of Total Project**

* 12,016 ft of water main installed (55% of total water main for the project)

**Issues Encountered/Notices**

* Roads where mains are being installed will be closed to thru traffic, but will remain open to local residents, school buses and emergency vehicles.
* OCE will continue to coordinate with residents regarding service line construction/easements.

**Work Anticipated for Week of December 18, 2017 through December 22, 2017**

* Water service crew will begin services to the residents on Matt Drive (assuming pressure, leakage and WQ testing all passes)
* Continue directional drill on Riverside Drive.
* Water main crew will continue installing water main pipe on Riverside.
* Contractor plans to connect residents on Matt Drive the week of Christmas.