**Village of Bennington Water Distribution Extensions**

**Weekly Update**

**Work Completed - Week of October 30, 2017 through November 3, 2017**

**Murphy Road**

* Road cleaned up, and stabilized for the winter is continue.

**Ore Bed Road**

* Main line installation completed this week.
* Road clean up started this week

**Harrington Road**

* Main line crew mobilized midweek.
* Main line installation began on Friday November 3, 2017.

**Park Street**

* Drilling and blasting was conducted throughout the week.

**Total Water Main Installed this Week**

* 845 ft

**Water Main Installed To Date and % of Total Project**

* 3,593 ft of water main installed (17% of total water main for the project)

**Issues Encountered/Notices**

* Roads where mains are being installed will be closed to thru traffic, but will remain open to local residents, school buses and emergency vehicles.
* OCE will coordinate with residents regarding service line construction.

**Work Anticipated for Week of November 6, 2017 through November 10, 2017**

* Water main crew will continue installing pipe on Harrington Road, and begin water main installation on Park and River Streets.
* Water service lines will begin on Murphy and Ore Bed Road. Services will be brought into the homes but not connected. Connection will be made next year.
* Drilling and blasting to continue of Park Street.
* Murphy and Ore Bed Road cleanup will continue in preparation for winter.