## MCM Reporting
Minimum Control Measure Reporting
GP Part 6.2 | MCM Requirements | Measurable Goal | Description of how requirement was met | List attachments if applicable | Activities planned for next year | Proposed change in BMP or measurable goal?
MM#1: Public Education and Outreach on Stormwater Impacts
1.c. (1) | Website maintained with locally relevant stormwater information | 409 site visits and 1,079 page views. | http://www.fcsvt.org/; https://stalbanstown.com/departments/stormwater_utility/index.php . Updated website and developed content. | N/A | N/A | No
1.c (2) | Maintain a program to identify opportunties and provide technical assistance on Low Impact BMPs | Number of visits to technical asst. pages. | Total page views to the following pages: - Workshops page: 89 - Resources: 65- Issues: 62 - Events: 55- Solutions: 53 New content added: - Photo Gallery of past events - FCS logo to website header | Franklin County Stormwater RSEP Report. | Perform annual updates, development of new content. | No
1.c (3) | Participate in a regional stormwater education strategy or develop an MS4 specific program | Franklin County Stormwater is the City/Town RSEP, administered by NRPC. | The Town pays $7,000 annually to this effort. In addition to web visits reported above, the RSEP participates in production of online videos and collaboration with organizations, like the St. Albans Museum, which bring in additional funds for educational programming. | Franklin County Stormwater RSEP Report. | Perform annual updates, development of new content. | No
| Other: Perform marketing and advertising of the Program in various media | Provide regular updates on social media accounts and mailings. | 10 Brochures were available to the public from the municipal office. The RSEP aimed to engage local news media in events with press releases throughout the year as well as utilize the available resources for sharing information with the communities such as 13 Front Porch Forum, Facebook and municipal websites. 141 social media posts, 21 News stories | Franklin County Stormwater RSEP Report. | Perform annual updates, development of new content. | No
| Other: Coordination with educators and organizations that can provide educational programing on curriculum resources and programming | Number of schools, teachers or students that participated Number of educational materials/lessons distributed | 346 4th graders participated in Lake Lessons over 5 days from 6 schools in St. Albans City and Town, Swanton, Highgate, Fairfield, and Georgia. There were 5 stations with educational content as well as an opening and closing activity. | Franklin County Stormwater RSEP Report. | We are hopeful that Lake Lessons will again be active. | No
MM#2: Public Involvement and Participation
2.d | Participate in a regional stormwater public involvement and participation strategy or develop an MS4 specific program | Participation, financial support; number of participants and/ or persons contacted | Quarterly meetings with RSEP to determine goals and budget. See attachment for MCM#2. | Franklin County Stormwater RSEP Report. | Continuing support for RSEP | No
2.d (2) | Events to engage the public. | Number of events offered and participants engaged. | Butt Litter Pick-up stats: 9 events- 170 participants- 34,483 butts collected. Outdoor Cleanup Stats: 33 volunteers -3 truck beds full of trash | Franklin County Stormwater RSEP Report. | Green Up Day, Coordinate 2-3 events/ guest lectures | No
2.d (2) | Recruitment of Volunteers and Partners | Number of participants engaged. | 218 volunteers attended FCS-led or sponsored events.Partner: FNLC, ECO AmeriCorps, MRBA, FCNRCD, Franklin Grand Isle Tobacco Coalition, St. Albans Museum, LCBP, and VPIRG. | Franklin County Stormwater RSEP Report. | Green Up Day | No
| Other: Storm drain stenciling project | Number of catch basins stenciled. | Public Works staff stenciled 50 catchbasins. | N/A | Continue practice | No
MM#3: Illicit Discharge Detection and Elimination
3.a (1) | Develop and maintain a GIS or AutoCAD map of the storm sewers in the regulated MS4 showing all outfalls | Maintain updated map that includes inventory of system. | The Town purchased the licensing for GIS ArcPro and has made substantial developments in mapping storm lines, outfalls, STPs and structures in the town. This effort is continually ongoing. | N/A | Perform additional mapping | No
3.a (2) | Develop ordinace or policy prohibiting non-stormwater discharges and implement enforcement procedures | Report enforcement actions taken under Ordinance, | The Town of St. Albans Stormwater Utility Ordinance was approved by the Select Board on September 21, 2020. The Stormwater Utility Ordinance was updated on May 22, 2022. | Stormwater Ordinance | Review current ordinance | No
3.a (3) | Develop and implement a plan to detect and address non-stormwater discharges | Perform Initial Investigation Findings for IDDE | The Town contracted in 2021, Watershed Consultants to complete a IDDE survey of 42 outfalls, including 7 newly found outfalls. These locations were documented and entered into the digital database for this project. | End of Year Report 2021 |  | No
3.a (4) | Inform public on the dangers of illegal discharges | Ongoing | Support the RSEP to inform the public about improper disposal methods and non-stormwater discharges. IDDE info is included in the town's Stormwater Utility Ordinance Document, Section 2.8 and 2.9. | N/A | No | No
3.a (6) | Status of monitoring activities: |  | St Albans will continue to assess the stormwater drainage system within the regulated small MS4 areas and will inspect all outfalls once per permit cycle. | N/A | No | No
| Outfalls Inspected: | Number of outfalls inspected. | Watershed Consulting was contracted to complete IDDE survey of 42 outfalls (dry weather samples were collected at each). The group checked for e. coli, anionic surfactants, ammonia, chlorine, and flouride as well as pH, conductivity, and temperature. The condition of the outfall and the flow rate was also recorded in 2021. Additionally, DPW inspected 100 outfalls in 2023. | None | Testing to be continued | No
| Number of dry-weather samples taken: | Number of samples taken. |  | None | No | No
| Feet of storwmater drainage pipe inspected: | Number of feet camered. | No culverts were videoed in 2023. | N/A | Line pipe | No
| Discharges Detected: | Number of discharges detected. | Watershed Consulting found 6 outfalls that had results above the allowed thresholds. Additonal investigations in progress | None | Testing to be continued. | No
| Discharges Corrected: | Number of discharges corrected. | None in 2023 | N/A | No | No
Other
MM#4: Construction Site Stormwater Runoff Control
4.a (1) | Develop and implement procedures to ensure that construction activities undertaken by the MS4 are properly permitted | Ongoing. | The Stormwater Ordinance regulates development for proper stormwater management for public and private projects. The Stormwater Utility is building a flow chart to be used internally and for Site Review that will assist in permit compliance. | Stormwater Ordinance | Permitting Flowchart | No
| Number of permitted MS4 construction projects: | Number of projects constructed. | The focus this year was getting some projects designed. Tanglewood is at 90% plans. Gricebrook design has begun, but ran into an issue with siting a BMP. We are negotiating with the property owner to site the BMP. Clyde Allen Drive design is underway. |  | Tanglewood and Clyde Allen Drive Construction. | No.
4.a (2) | Review existing policies to determine effectiveness, consistency with state standards; Amend for consistency with state standards | Achieved | The Town evaluated its regulations to ensure that local post-construction stormwater standards are consistent with the State standards. | N/A | No | No
4.a (3) | Develop and implement ordinance that regulates earth distrubance <1ac | Ordinance has been approved | The approved Stormwater Utility Ordinance addresses erosion and sediment control provisions for earth disturbance of <1 acre. It includes requirements for projects that fall below the minimum regulatory threshold and are not subject to state erosion control requirements. | N/A | No | No
| Number of projects with <1ac of disturbance subject to MS4 requirements: | Number of projects constructed. | 16 projects were constructed in the Town | N/A | No | No
Other
MM#5: Post Construction Stormwater Management for New Development and Redevelopment
5.d | Review existing policies to determine effectiveness, consistency with state standards, opportuntities for LID, and opportunties for changes to street and parking requirements; Amend for consistency with state standards | Ordinance has been adopted. | Policy in Ordinance meets state standards. Developing additional language to add to the By Laws to provide surface water protection measures. | N/A | Continue periodic review of our Bylaws for compliance with MS4. | No
5.e | Develop and implement procedures to identify projects that disturb >1ac but do not require a state post-construction permit | Ordinance has been adopted. | Developed language to add to the Unified Development Bylaws to provide surface water protection measures. Stormwater Ordinance was adopted and includes a section on erosion and sediment control provisions for disturbances greater than 1 acre. | N/A | No | No
| Number of projects >1ac of disturbance <1ac of impervious: | Number of projects reviewed. | 16 projects were reviewed. | N/A | No | No
5.f | Adopt an ordinance or policy that requires projects that disturb >1ac to utilize a combination of structural, non-structural, and low impact BMPs and ensure long-term maintenance | Ordinance has been adopted. | Town has approved a Stormwater Utility Ordinance that addresses the requirement for post-construction stormwater management provisions for earth disturbance of >1 acre. | N/A | No | No
5.g (1) | Develop and implement procedures for inspecting projects subject to the MS4's ordinance | Ordinance has been adopted. | Town has approved a Stormwater Utility Ordinance that addresses the requirement for post-construction stormwater management provisions for earth disturbance of >1 acre. | N/A | No | No
| Number of STPs (without state permits) inspected by MS4: | Number of inspections performed. | Performed an inspection of the Town Rain garden located on Lake Road. | N/A | Continue inspection and maintanence. | No.
5.g (2) | Develop and implement procedures to ensure that development activities undertaken by the MS4 are properly permitted | Develop By Laws to protect Water Quality . | Developed language to add to the Unified Development Bylaws which provided surface water protection measures. | N/A | Approve By Laws. | No.
Other
MM#6: Pollution Prevention and Good Housekeeping for Municipal Operations
6.b (2) | Conduct stormwater training for staff | EPSC Training for Town crew. Number in attendence. | All staff attended numerous trainings through Vermont Local Roads on road management, stormwater BMPs, safety, etc. | N/A | Training for crew | No
6.b (3) | Implement controls for reducing or eliminating the discharge of pollutants from the MS4 |  | Town addressing roadside erosion control projects with construction of projects for the MRGP. The City of St. Albans completes street sweeping for both the town and city. | N/A. | Same | No.
| STPs constructed, upgraded, & maintained | Number of STPs | List in BMP tracking table
| STPs incorporated into the MS4 | Number of STPs | List in BMP tracking table
| Inspections performed on fleet vehicles, buildings, garages, parks, open spaces | Regular inspections. | Regular maintenance as needed. Materials on municipal properties are properly stored. | N/A. | Same | No.
| Catch basin cleaning | # of Basins | 301 catch basins inspected, and four catch basins were cleaned in 2023. | N/A. | Clean 1/4 of Town controlled CBs | No.
| Street Sweeping | Lane Miles | None | N/A. | Same | No.
| Leaf/organic waste removal program | Yards of debris collected | No leaf debris was collected by the Town. | N/A. | Same | No.
6.b (4) | Develop and implement procedures for proper disposal of wastes | Develop policy to direct staff. | Town will develop a policy for Handling Material Collected During Street Sweeping, Catch Basin and Storm Pipe Cleaning. | N/A. | Develop policy. | No.
6.c | Prohibit use of phosphorus containing fertilizers on facility operations unless warranted by a soil test; submit copy of test | Prohibition in place. | No use of fertilizer without soil testing; This has been previously addressed in maintenance and training program
6.d | Participate in the Agency's Municipal Compliance Assistance Program (or other audit program) for municipal garages | Document audit once per permit cycle | The Town contacted Project Worksafe to have them complete an inspection of our facility. Any deficiencies identified were corrected, and the facility is in good shape.
Other

## Additional Reporting
Additional MS4 Reporting Requirements
Annual Review of SWMP completed | Yes. Revised and submitted to ANR on March 26, 2024.
Results of information collected and analyzed, if not included elsewhere | N/A
Notice that permittee is relying on another entity to satisy some of its permit obligations | Northwest Regional Planning Commission: MCMs 1 and 2.
Estimated funds spent on stormwater management for the fiscal year* | 168621
Other information, if applicable | Budget is dependent on receiving grant funding to construct Tanglewood STP
Impaired Waters Response Plan
Impaired Stream | Rugg Brook, Stevens Brook
Impairment | Stormwater sediment.
Status of implementation | Pursuing implementation of FRP.
Planned activities for upcoming year | Construction of Tanglewood and Clyde Allen Drive STP projects, design Grice Brook STP, scoping studies for the West and East Basin Projects along the SASH.
Other information, if applicable
* Optional response.

## NonStructural BMPs
Non Structural BMP Reporting
Complete Table 1 or 2, depending on tracking method used by MS4
Table 1. Area tracking method |  |  |  | Table 2. Measurement of material tracking method | Table 3. Phosphorus Reduction Factor
Sub Area Name (Lake segment, route, etc.) |  |  |  | Combined dry weight of material collected (kg) |  | 2/year (spring and fall) | Monthly | Weekly | 4X in the fall
Area of streets swept (acres) | 1.9 | none |  | OR Cubic yards of material collected | Mechanical Broom | 1% | 3% | 5% | 17%
P Load from Streets where sweeping occurs (kg/year) | 20 | n/a |  | Number of sediment samples taken | Vacuum Assisted | 2% | 4% | 8% | 17%
Sweeper Frequency | 2/year (spring and fall) |  |  | Lab where samples were processed | High Efficiency Regenerative Air-Vacuum | 2% | 8% | 10% | 17%
Sweeper Technology | Mechanical Broom |  |  | Record the average TP result
Year sweeping started | 2019 |  |  | Was a particle size analysis done?
If weekly or monthly, number of months streets are swept |  |  |  | Please attach results from the lab
Phosphorus Credit | 1%
Phosphrous Reduction from Street Sweeping (kg/year) | 0.2 |  |  | **There is currently no approved accounting methodology based on weight or volume of material collected. Should a method be developed, DEC anticipates information like that in Table 2 could be required.
Catch Basin Cleaning
P Load from Streets where catch basin cleaning occurs (kg/year)
Phosphorus Credit | 2% | 2% | 2%
Phosphrous Reduction from Catch Basin Cleaning(kg/year)

## FRP Implementation
Flow Restoration Plan Implementation
| Rugg Brook | Stevens Brook
Summary of actions taken to implement FRP components | Tanglewood BMP final design is at 100%. Seeking one easement for the project, then we are ready to go out to bid. Clyde Allen Drive STP is currently in final design; Grice Brook Retirement Community STP is in preliminary engineering. Seeking funding for scoping studies for the East and West Basin projects in the SASH. | Grice Brook Retirement Community STP is currently in preliminary engineering.
Extent of BMP implemention | Design | Design
Estimate of the extent of completion for remaining items | No other BMPs were advanced in 2021. Still numerous projects to advance in the next decade. The Town has completed the PCP. | No other BMPs were advanced in 2021. Currently working on projects in the Rugg Brook Watershed.
Assessment of ability to meet outstanding schedule items | The Town started a Stormwater Utility in 2021which will allow for the targeted schedule to be achieved. | The Town started a Stormwater Utility in 2021which will allow for the targeted schedule to be achieved.
Stream Flow Monitoring
Participate in MOU with VTDEC to monitor sw impaired streams | Program no longer required
Funds spent on stream flow monitoring in 2021 | Program no longer required
Steam Corridor Protection
Ordinance or regulation adopted to protect and regulate development in sw impaired water stream corridors | https://cms7files.revize.com/stalbansvt/Stormwater%20Utility%20Ordinance%20Recorded%2011.20.20.pdf

## PCP Development
Phophorus Control Plan Development
Extent of implementation of the Municipal Roads Standards
Road Erosion Inventory (REI) | Uploaded to 'Municipal Roads General Permit Implementation Table'
Map and identify connected curbed and catch basin road segments to specified outlets | Road Erosion Inventory is complete.
Roads and Outlets planned for upgrade within the first permit term (through July 2023) | Roads and culverts to be repaired and upgraded as necessary.
Roads and Outlets planned for upgrade in calendar year 2023. | DPW will continue to replace culverts (when needed) on roads being paved in current paving cycle. Preliminarily, French Hill Road, Kellogg Road, Congress Street, Westview, and Eastview Road have been identified.
Extent of street sweeping and catch basin cleaning | None done in 2023
Extent of stormwater BMP implementation | See 'BMP Tracking Table'
Estimate of the extent of remaining items requiring completion | PCP completed in spring 2022. Numerous projects identified.
Assessment of the ability to meet outstanding schedule items | PCP and FRP projects are going to require a lot of outside funding in order to complete them all.
List of '3 acre sites' that have been taken over by the MS4
Has this acreage been included in the MS4's baseload calcuations? | Yes
Has the baseload been calculated based on municipally owned and controlled developed lands? | Yes
Summarize progress on establishing P credits for existing projects | Completed
Summarize progress on identifying additional projects necessary to meet the PCP targets | Completed