## MCM Reporting
Minimum Control Measure Reporting
GP Part 6.2 | MCM Requirements | Measurable Goal | Description of how requirement was met | List attachments if applicable | Activities planned for next year | Proposed change in BMP or measurable goal?
MM#1: Public Education and Outreach on Stormwater Impacts
1.c. (1) | Website maintained with locally relevant stormwater information | Maintain the website with current information related to the Municipal Stormwater Program minimizing the time the website is unavailable for maintenance, or other reasons. | The Town maintains a stormwater specific website page that provides locally relevant information. https://www.town.williston.vt.us/index.asp?Type=B_BASIC&SEC={ACC6B21E-0FDB-497F-8A5A-62CDFF871272} |  | Continue to maintain Town website | The measurable goal for this MCM was changed from visitor count to maintain the site with minimum number of days the site is unavailable due to maintenance or other outages. The reason for the change is the website serves multiple departments and counts specific to the website page was unobtainable.
1.c (2) | Maintain a program to identify opportunties and provide technical assistance on Low Impact BMPs |  | As part of the Bylaws, developments which will disturb less than 1/2 acre are still required to mitigate erosion and sediment migration from the project site. Applicants are provided a Low Impact Runoff & Erosion Control Checklist to provide guidance on types of BMP's that should be evaluated, and technical assistance is provided by staff when requested.
1.c (3) | Participate in a regional stormwater education strategy or develop an MS4 specific program | Participate in a regional stormwater education strategy | $7,000 was paid to Rethink Runoff to assist with outreach and education. The results of the outreach efforts are provided in Appendix A. | Appendix A: Rethink Runoff Annual Report | Continue to work with Rethink Runoff. | No changes are proposed
Other
MM#2: Public Involvement and Participation
2.d | Participate in a regional stormwater public involvement and participation strategy or develop an MS4 specific program | Participate in a regional stormwater public involvement and participation strategy | The Town participated in the Rethink Runoff Stream Team program, including participation in the steering committee for the program. | Appendix B: Stream Team Summary | Continue to partner with CCRPC, Rethink Runoff, and Stream Team. | No changes are proposed
Other
MM#3: Illicit Discharge Detection and Elimination
3.a (1) | Develop and maintain a GIS or AutoCAD map of the storm sewers in the regulated MS4 showing all outfalls | Make available a GIS map of known stormwater sewer lines and outfalls located within the regulated MS4 area. | The Town of Williston contracted Aldrich & Elliot to develop a GIS file containing the known locations of storm sewers and outfalls located in the MS4 regulated area. This file is continually updated as new infrastructure is discovered, constructed, or relocated. |  | Continue with current practices. | No changes are proposed.
3.a (2) | Develop ordinance or policy prohibiting non-stormwater discharges and implement enforcement procedures | Adopt an ordinance prohibiting non-stormwater discharges, and enforcement procedures | In May, 2015, the Williston Select Board adopted the Stormwater Ordinance which prohibits the discharge of non-stormwater to the MS4 and provides an enforce mechanism for non-compliance. A copy of the ordinance can be found on the Town's Stormwater webpage. |  | Continue with current practices. | No changes are proposed.
3.a (3) | Develop and implement a plan to detect and address non-stormwater discharges | Assess known public outfalls for potential illicit connections or non-stormwater discharges once per permit cycle | No outfalls were inspected during 2023. Williston utlilizes a digital form that can be filled out in the field. Priority areas have been identified for future outfall inspections. |  | Continue with current practices | No changes are proposed.
3.a (4) | Inform public on the dangers of illegal discharges | Number of outreach brochures handed out | Town of Williston utilizes an outreach brochure on an as needed basis in neighborhoods where illicit discharges are discovered. During the outfall assessment process no suspect illicit connections or non-stormwater discharges were identified so no outreach brochures were utilized. |  | Continue with current practices | No changes are proposed.
3.a (6) | Status of monitoring activities: | Provide the Secretary with an annual report including number of discoveries or complaints, number resolved, number of water quality test conducted or samples collected. | Outfall inspections are performed routinely and in response to complaints received. |  | Continue with current practices | No changes are proposed.
| Outfalls Inspected: |  | 0
| Number of dry-weather samples taken: |  | 0
| Feet of stormwater drainage pipe inspected: |  | 0
| Discharges Detected: |  | 0
| Discharges Corrected: |  | 0
Other
MM#4: Construction Site Stormwater Runoff Control
4.a (1) | Develop and implement procedures to ensure that construction activities undertaken by the MS4 are properly permitted | Number of permitted MS4 construction Projects | Capital Improvement Projects which are not outsourced to qualified companies are undertaken by staff trained in the field of work being performed. Additionally, the states Environmental Notice Bulletin is monitored for compliance with this policy. |  | Continue to implement the program | No changes are proposed
| Number of permitted MS4 construction projects: | 0
4.a (2) | Review existing policies to determine effectiveness, consistency with state standards; Amend for consistency with state standards | Review and amend as needed by end of permit term (2028) | Current policies were reviewed and found to be effective and consistent with state standards. Existing policies will continue to be reviewed on an ongoing basis and improved as deemed necessary and in compliance with permit requirements. |  | Review Ch. 29 and make updates, if needed, to ensure it aligns with State guidelines. | No changes are proposed
4.a (3) | Develop and implement ordinance that regulates earth disturbance <1ac | Implement Ordinance | Town of Williston Development Bylaw, Chapter 29: Watershed Health |  | Continue to implement the program | No changes are proposed
| Number of projects with <1ac of disturbance subject to MS4 requirements: | Total project count: 4 | 1/4-1 acre. Less than 1/4 acre was not subject to MS4 requirements specific to construction sites.
Other
MM#5: Post Construction Stormwater Management for New Development and Redevelopment
5.d | Review existing policies to determine effectiveness, consistency with state standards, opportunities for LID, and opportunities for changes to street and parking requirements; Amend for consistency with state standards | Review and amend as needed by end of permit term (2028) | Town of Williston Bylaws were reviewed and found to contain language that encourages use of low impact design “to the maximum extent practical given the sites soil characteristics, slope and other relevant factors”. These provisions will continue to be reviewed and improved as deemed necessary and in compliance with permit requirements. |  | Continue to implement the program | No changes are proposed
5.e | Develop and implement procedures to identify projects that disturb >1ac but do not require a state post-construction permit |  | A state post-construction permit may be required for projects which construct, or reconstruct, one acre or more of impervious surface(s).The Williston Development Bylaws requires the submittal of an application for new development and redevelopment activities. Through the application processes, the area of disturbance and area of impervious surfaces is reviewed for projects which may require a state post-construction permit, but the requirement for obtaining the appropriate State, Federal, or other agency permits is the responsibility of the developer/owner. |  | Continue to implement the program | No changes are proposed
| Number of projects >1ac of disturbance <1ac of impervious: | 1
5.f | Adopt an ordinance or policy that requires projects that disturb >1ac to utilize a combination of structural, non-structural, and low impact BMPs and ensure long-term maintenance | Adopt Ordinance | Town of Williston Development Bylaw, Chapter 29: Watershed Health and the Ordinance for Regulating Use of Public and Private Stormwater Systems. |  | Review Ch. 29 and the Stormwater Ordinance to make updates, if needed, to ensure it aligns with State guidelines. | No changes are proposed
5.g (1) | Develop and implement procedures for inspecting projects subject to the MS4's ordinance |  | Projects are periodically inspected by staff to verify compliance MS4 Ordinances. |  | Continue to implement the program | No changes are proposed
| Number of STPs (without state permits) inspected by MS4: | 0
5.g (2) | Develop and implement procedures to ensure that development activities undertaken by the MS4 are properly permitted |  | Development undertaken by the MS4 are either performed or overseen by staff knowledgeable in local and state regulations relevant to the work being performed, and all required permits are obtained as standard practice. |  | Continue to implement the program | No changes are proposed
Other
MM#6: Pollution Prevention and Good Housekeeping for Municipal Operations
6.b (2) | Conduct stormwater training for staff |  | Attended conferences and stormwater specific trainings throughout the year |  | Continue to attend trainings | No changes are proposed
6.b (3) | Implement controls for reducing or eliminating the discharge of pollutants from the MS4 |  | There are a network of Stormwater Treatment Practices implemented through out the Town which are listed in more detail in the BMP Tracking Table. The Town's Department of Public Works also implements practices to minimize the use of salt on Town maintained roads.
| STPs constructed, upgraded, & maintained |  | List in BMP tracking table
| STPs incorporated into the MS4 |  | None this year.
| Inspections performed on fleet vehicles, buildings, garages, parks, open spaces |  | Vermont League of City's and Town's performs an annual inspection of facilites, in addition to the Stormwater Coordinator performing inspections of Municiple owned lands.
| Catch basin cleaning |  | Complete 'Non Structural Tab'
| Street Sweeping |  | Complete 'Non Structural Tab'
| Leaf/organic waste removal program |  | Complete 'Non Structural Tab'
6.b (4) | Develop and implement procedures for proper disposal of wastes |  | Waste collected from Street Sweeping, Catch Basin Cleaning, and STP maintenance is stagged at a Town owned parcel for testing prior to reuse or disposal. |  | Continue to implement the program | No changes are proposed
6.c | Prohibit use of phosphorus containing fertilizers on facility operations unless warranted by a soil test; submit copy of test |  | Facilities does not use fertilizers containing Phosphorus unless warranted by a soil test. |  | Continue to implement the program | No changes are proposed
6.d | Participate in the Agency's Municipal Compliance Assistance Program (or other audit program) for municipal garages |  | Public Work Facility and other Municipal buildings are inspected annually through the PACIF and annual stormwater treatment practice inspections. |  | Continue to implement the program | No changes are proposed
Other

## Additional Reporting
Additional MS4 Reporting Requirements
Annual Review of SWMP completed | Yes
Results of information collected and analyzed, if not included elsewhere | The SWMP was reviewed and updated to meet the requirements of the new General Permit for Stormwater Discharges from Regulated Municipal Separate Storm Sewer Systems (MS4s) and Certain Developed Lands.
Notice that permittee is relying on another entity to satisfy some of its permit obligations | Chittenden County Regional Planning Commission is the lead agency for the activities required to meet Minimum Measure #1 & #2.
Estimated funds spent on stormwater management for the fiscal year*
Other information, if applicable
Impaired Waters Response Plan
Impaired Stream | Allen Brook | Muddy Brook Trib. 4 and Trib. to Trib. 4
Impairment | Stormwater | Chloride
Status of implementation | Adopted | Adopted
Planned activities for upcoming year | Provide support to the remaining communities upgrading their Stormwater Treatment Practices to meet the Allen Brook Flow Restoration Plan requirements. Continue with street sweeping and catch basin cleaning. | Continue chloride reduction practices outlined in the Salt Reduction Plan, which was incorporated into the updated SWMP.
Other information, if applicable
* Optional response.

## NonStructural BMPs
Non Structural BMP Reporting
Complete Table 1 or 2, depending on tracking method used by MS4
Table 1. Area tracking method |  |  |  | Table 2. Measurement of material tracking method | Table 3. Phosphorus Reduction Factor
Sub Area Name (Lake segment, route, etc.) | Curbed Roads located within the MS4. |  |  | Combined dry weight of material collected (kg) |  | 2/year (spring and fall) | Monthly | Weekly | 4X in the fall
Area of streets swept (acres) | 85.82 Acres (approximately 24 miles with average width of 30' ) |  |  | OR Cubic yards of material collected | Mechanical Broom | 1% | 3% | 5% | 17%
P Load from Streets where sweeping occurs (kg/year) | 68.83 | Load Rate = 0.802 (kg/acre/yr) |  | Number of sediment samples taken | Vacuum Assisted | 2% | 4% | 8% | 17%
Sweeper Frequency | 2/year (spring and fall) |  |  | Lab where samples were processed | High Efficiency Regenerative Air-Vacuum | 2% | 8% | 10% | 17%
Sweeper Technology | High Efficiency Regenerative Air-Vacuum |  |  | Record the average TP result
Year sweeping started | 2008 |  |  | Was a particle size analysis done?
If weekly or monthly, number of months streets are swept |  |  |  | Please attach results from the lab
Phosphorus Credit | 2%
Phosphorus Reduction from Street Sweeping (kg/year) | 1.3766 |  |  | **There is currently no approved accounting methodology based on weight or volume of material collected. Should a method be developed, DEC anticipates information like that in Table 2 could be required.
Catch Basin Cleaning
P Load from Streets where catch basin cleaning occurs (kg/year)
Phosphorus Credit | 2% | 2% | 2%
Phosphorus Reduction from Catch Basin Cleaning(kg/year)

## FRP Implementation
Flow Restoration Plan Implementation
Allen Brook
Summary of actions taken to implement FRP components | Continue to support the upgrade and renewal of expired stormwater discharge permits required for stormwater treatment systems serving residential communities. Continue with sweeping and catch basin cleaning programs.
Extent of BMP implementation | To date, all but one residential stormwater treatment practice has been upgraded as required by the FRP.
Estimate of the extent of completion for remaining items | 5%
Assessment of ability to meet outstanding schedule items | There are ongoing conversations between the Town and the State concerning at least one stormwater treatment practice identified in the Plan which has not received authorization from the State's Wetlands program, and cannot be constructed without said permission.
Stream Flow Monitoring
Does your municipality conduct stream flow monitoring? | No
Steam Corridor Protection
Ordinance or regulation adopted to protect and regulate development in sw impaired water stream corridors | https://www.town.williston.vt.us/vertical/sites/%7BF506B13C-605B-4878-8062-87E5927E49F0%7D/uploads/WDB_Oct_15_2019_Chapter_29_Watershed_Health.docx.pdf

## PCP Development
Phosphorus Control Plan Development (PCP)
Road Erosion Inventory (REI) | Uploaded to 'Municipal Roads General Permit Implementation Table'
Are there any segments on the MRGP Implementation Table portal that are incomplete? If so, please describe how the data will be completed. | Yes, incomplete data was recorded during the Initial REI inventory due to Outfalls and segments located on private property, and/or access was restricted due to private property. Incomplete data will be resolved as part of the re-inventory process.
Roads and Outlets planned for upgrade in calendar year 2024. | If these have not been identified in the Implementation Table, to the best of your ability, list them here.
Extent of street sweeping and catch basin cleaning | See 'Non-structural tab'
Extent of stormwater BMP implementation | See 'BMP Tracking Table'
What is the MS4's overall status in implementing the PCP? | Implementation in progress.
Assessment of the ability to meet outstanding schedule items | The remaining projects are pending permit approval or funding. PCP may need to be updated if remaining projects are unable to move forward due to permitting issues or funding restrictions.
List of '3 acre sites' that have been taken over by the MS4 in the past calendar year. | None.
Has the additional loading from privately owned land associated with the 3-acre sites been addressed in the phosphorus control plan? If not describe the MS4s plan to address the additional target.