## MCM Reporting
Minimum Control Measure Reporting
GP Part 6.2 | MCM Requirements | Measurable Goal | Description of how requirement was met | List attachments if applicable | Activities planned for next year | Proposed change in BMP or measurable goal?
MM#1: Public Education and Outreach on Stormwater Impacts
1.c. (1) | Website maintained with locally relevant stormwater information | Report number of website visitors, and other web statistics. The website provides stormwater project information and updates. | • www.sburlstormwater.com •The City's analytics tool stopped logging traffic in 2021. No activity was recorded in 2022. This problem has now been addressed and rectified as of March 2023. During this time the City's website continuted to be operational and project information was routinley updated, despite the Google analytics tool being down. |  | Continue to maintain publicly accessible web service with up to date GIS data
1.c (2) | Maintain a program to identify opportunties and provide technical assistance on Low Impact BMPs | Enforce requirements in the City LDRs that require development to use infiltration practices and LID strategies. | • The City's stormwater section reviews all plans submitted for development review to ensure compliance with stormwater managment sections of the Land Development Regulations (LDRs), which requires infiltrating the Water Quality storm event, if feasable. |  | Continue to review plans and enforce City's land development regulations.
1.c (3) | Participate in a regional stormwater education strategy or develop an MS4 specific program | Participate in and financially support Rethink Runoff; survey residents every 5 years; provide summary of steering committee activities, web statistics, and total financial contributions to regional program. | • Chittenden County MS4s retained the services of design company Pluck to generate advertising content under the campaign Rethink Runoff. • Advertising work included ads on: YouTube, Google, VTDigger, VPR, WVMT, Front Porch Forum, Facebook and Instagram. • Facebook/Instagram had 2,816 interactions, Facebook had 25 new likes, Instgrame had 523 followers, website (rethinkrunoff.org) had 13,916 visits. • Paid $6,000 in FY23 annual dues to ReThink Runoff (formly RSEP and CCST). | Appendix A | Continue to participate in Rethink Runoff Program
Other
MM#2: Public Involvement and Participation
2.d | Participate in a regional stormwater public involvement and participation strategy or develop an MS4 specific program | Participate in Rethink Runoff, report on activities including the number of volunteers that participated in stormwater related events and the City's financial contributions. | Chittenden County MS4s retained the Winooski Natural Resources Conservation District to run the Rethink Runoff Stream Team (RRST). • RRST published six newsletters with 768 subscibers. • Three outreach events were held in 2023 and consisted of tabling efforts at a LCBP presentation in Milton, Explore Essex event, Colchester Corner Annual Autumn Market. • Four hands-on volunteer events were held in which 198 people participated. • The City's annual financial contribution was $6,000 paid to Rethink Runoff. | Appendix B | Continue to participate in Rethink Runoff Stream Team program.
| Storm Drain Stenciling program | Report on number of new "No Dumping" labels put in place. | • 262 "No Dumping" labels painted on storm drains |  | Continue catch basin cleaning and inspection program.
MM#3: Illicit Discharge Detection and Elimination
3.a (1) | Develop and maintain a GIS or AutoCAD map of the storm sewers in the regulated MS4 showing all outfalls | Maintain a storm sewer systems map (GIS) and report the number of stormwater drainage structures, miles of stormwater conveyance, and stormwater outfalls within the City. | The City maintains a GIS map of its storm sewer system in ESRI's ArcPro and ArcGIS Portal. Crews use iPads with Collector and Survey-123 to complete outfall inspections. Outfall locations are confirmed using the GPS of the iPad to field verify accuracy of points. Outfall points can be manually adjusted in the field to correct locations. New outfall locations are added to the map after neighborhoods/projects are constructed by georeferencing as-built plans. • 3418 drainage structures owned/maintained by the City. • 95 miles of stormwater conveyance owned/maintained by the City. • 210 outfalls owned/maintained by the City. |  | Continue to maintain City's GIS map with storm sewer information, including outfalls
3.a (2) | Develop ordinace or policy prohibiting non-stormwater discharges and implement enforcement procedures | Continue enforcement of City Ordinance, review ordinance within 3 years. | The South Burlington Sewer and Stormwater Ordinance and Stormwater Upgrade Feasibility Analysis ordinance were updated in 2022. No further updates were made in 2023. |  | The City will continue to enforce the existing Stormwater Ordinance and make further updates in the future as needed.
3.a (3) | Develop and implement a plan to detect and address non-stormwater discharges | Video inspections: Report the linear feet of pipe inspected each year. Outfall inspections: Inspect no less than 50% of the City-owned outfalls each year | 815 LF of pipe were inspected with the camera in 2023. A total of 219 outfall inspections were completed in 2023. | Appendix C | The City will continue to inspect outfalls and investigate illicit discharges.
3.a (4) | Inform public on the dangers of illegal discharges | City will dedicate a section on its stormwater website to illicit discharge detection and elimination success stories. | The City maintains a link on our Stormwater Project folder on our website with information pertaining to Illicit discharges. (http://sburlstormwater.com/stormwater-projects/) |  | The City will continue to update the website as needed.
3.a (6) | Status of monitoring activities: | Track the number of illicit discharges encountered and eliminated. | 1 illicit discharge was detected in 2023, a sewer main collapsed and the Hinesburg Rd pump station backed up and discharged to Potash Brook, this was corrected as quickly as possible. |  | Continue to report and record illicit discharges to the State.
| Outfalls Inspected: | Inspect no less than 50% of City-owned stormwater outfalls each year. | • 219 outfall inspections were completed, including 128 closed pipe outfalls and 91 open channel outfalls. | Appendix C | Continue to complete outfall inspection program and camera storm drains as needed.
| Number of dry-weather samples taken: | Report number of outfall samples collected. | No dry weather samples were taken, as no illicit connections were suspected. |  | Continue to take samples for any suspected illicit connections.
| Feet of storwmater drainage pipe inspected: | Report linear feet of pipe inspected via video inspection program. | 815 LF of pipe were inspected with the camera in 2023. |  | Continue to viedo storm drains to inspect for illicit connections as needed.
| Discharges Detected: | Report the number of discharges detected. | 1 illicit discharge was detected in 2023. |  | Continue to report and record illicit discharges to the State.
| Discharges Corrected: | Correct illicit discharges detected. | 1 illicit discharge was corrected in 2023, with the repair of a broken sewer main. |  | Continue to correct illicit discharges as needed.
| Coordination with drinking water suppliers | Before the end of the permit cycle the City will meet with CWD to review their BMPs relating to discharges of drinking water to the MS4. | • CWD has indicated that they have practices in place for annual flushing of hydrants, where the water is dechlorinated and then discharged to a grassed area, rather than a catch basin, where possible. • CWD has developed a sediment control policy as part of their emergency response procedures for water main breaks. This includes placement of filter fabric under catch basin grates if the water cannot be shut off immediately. Prioritization is given to shutting off the water first, in order to stop the source of the erosion. |  | The City will continue to meet with CWD at least once per permit cycle to review BMPs related to discharges of drinking water to the MS4.
MM#4: Construction Site Stormwater Runoff Control
4.a (1) | Develop and implement procedures to ensure that construction activities undertaken by the MS4 are properly permitted | Enforce the existing LDRs pertaining to Construction and Erosion Control Standards. | • The City continues to ensure that construction activities undertaken by the City are properly permitted. |  | The City will continue to enforce the existing LDRs pertaining to Construction and Erosion Control Standards.
| Number of permitted MS4 construction projects: | Report summary of projects that exceeded 1 acre of disturbance. | A total of ten (10) projects exceeded 1 acre of disturbance, see Appendix D for a summary. | Appendix D | The City will continue to report summary of projects that exceeded 1 acre of disturbance.
4.a (2) | Review existing policies to determine effectiveness, consistency with state standards; Amend for consistency with state standards | Enforce Article 16 (Construction and Erosion Control Standards) of the LDRs. | The City's Land Development Regulations, Article 16. Construction and Erosion Control Standards grants superseding authority to the Vermont Department of Environmental Conservation, as to ensure there are no conflicts between local and state standards. These will be reviewed in 2024 to ensure continuing consistency. |  | The City will continue to review Land Development Regulations to ensure they are consistent with State standards.
4.a (3) | Develop and implement ordinance that regulates earth distrubance <1ac | Enforce Article 16 (Construction and Erosion Control Standards) of the LDRs. | The City's Land Development Regulations, Article 16. Construction and Erosion Control Standards apply to all projects and does not establish an exemption threshold. |  | Ordinance has been established.
| Number of projects with <1ac of disturbance subject to MS4 requirements: | Report the number of projects with <1 acre of disturbance subject to MS4 requirements. | A total of twenty-three (23) projects were required to submit site plan applications with less than 1 acre of disturbance and were subject to the City's EPSC requirements, see Appendix D. | Appendix D | The City will continue to report the number of projects with <1 acre of disturbance subject to MS4 requirements.
| Construction BMP handout | Number distributed | In total, 200 erosion control brochures were distributed in 2023. All proprty owners are subject to the City's Stormwater and Sewer Ordinance, which prohibits illicit discharges. In 2023 there were 220 zoning permits issued in the City of South Burlington for projects that entailed any amount of ground disturbance (new construction, decks, additions, sheds, pools, etc.) All projects that included ground disturbance were provided with an erosion control borchure. |  | The City will continue to distribute Erosion Control Brochures with every zoning permit issued.
| Construction site inspections | Number of construction site inspections. | 18 Construction Site inspections were recorded in 2023 | Appendix E | Continue to inspect construction sites.
MM#5: Post Construction Stormwater Management for New Development and Redevelopment
5.d | Review existing policies to determine effectiveness, consistency with state standards, opportuntities for LID, and opportunties for changes to street and parking requirements; Amend for consistency with state standards | Enforce LDRs, evaluate requirements and determine if changes are necessary. | The City continues to enforce the LDRs. No changes pertaining to stormwater were enacted in 2023. The LDRs are expected to be revised in 2024 for consistency with the new 2023 MS4 permit. |  | The City will continue to review Land Development Regulations to ensure they are consistent with State standards.
5.e | Develop and implement procedures to identify projects that disturb >1ac but do not require a state post-construction permit | Enforce LDRS. | The City's Land Development Regulations, Article 16. Construction and Erosion Control Standards apply to all projects and does not establish an exemption threshold. |  | The City will continue to enforce the existing LDRs pertaining to Construction and Erosion Control Standards
| Number of projects >1ac of disturbance <1ac of impervious: | Report the number of projects with >1ac of disturbance and <1ac of impervious | A total of two (2) projects met this criteria, see Appendix D. | Appendix D | The City will continue to report the number of projects with >1ac of disturbance and <1ac of impervious
5.f | Adopt an ordinance or policy that requires projects that disturb >1ac to utilize a combination of structural, non-structural, and low impact BMPs and ensure long-term maintenance | Enforce LDRs | Every site plan reviewed by Stormwater Staff includes comment recommending the DRB to include a condition that the applicant regularly maintain all stormwater treatment and conveyance infrastruture. Property owners who do not comply with this condition are subject to zoning violation enforcement. |  | The City will continue to enforce the existing LDRs pertaining to post-construction stormwater management.
5.g (1) | Develop and implement procedures for inspecting projects subject to the MS4's ordinance | Enforce LDRs | Projects subject to the City's Land Development Regualtions found to be in violation of their maintenance condition are subject to zoning enforcement procedures. |  | The City will continue to enforce zoning requirements.
| Number of STPs (without state permits) inspected by MS4: | Report number of STPs inspected that do not have State permits | 13 STPs were inspected that do not have State permits |  | The City will continue to inspect STPs subject to the MS4's ordinance
5.g (2) | Develop and implement procedures to ensure that development activities undertaken by the MS4 are properly permitted | Enforce LDRs | All internal Stormwater program projects are reviewed with all necessary permitting agencies and all applicable permits are obtained. For all other City projects, Stormwater Staff review projects and provide comments that require the project receive all necessary State permits. |  | The City will continue to ensure that development activities are properly permitted.
| Maintain an updated list of STPs covered by the MS4's permit authorization | Report on new STPs built by the City and STPs incorporated into the MS4 permit | In 2023, the City wrapped up construction on Burlington Country Club (PB0056) and Lindenwood (PB0050). Construction began on Kennedy Drive Pond 2 (PB0041) and will wrap up in 2024. Permit 8410-9015 was rolled into the City's MS4 in 2023. | Appendix F | In 2024, the City anticipates finishing construction on the Kennedy Drive Pond 2 Expansion (PB0041). Permit 3153-9050 will be rolled into the City's MS4 in 2024.
| Inspect and ensure maintenance of all STPs covered by the MS4's permit authorization | Inspect STPs at least twice per year, report # of inspections | 93 STP inspections were completed in 2023 |  | The City will continue to inspect all of its STPs at a minimum of twice per year.
| Assist ANR with stormwater permitting program | Provide a summary of projects that will create 1 or more acres of impervious area | A total of eight (8) projects were approved that will create 1 or more acres of impervious. A summary of these projects can be found in Appendix D. | Appendix D | The City will continue to provide a summary of projects that create 1 or more acres of impervious area
MM#6: Pollution Prevention and Good Housekeeping for Municipal Operations
6.b (2) | Conduct stormwater training for staff | List of attendees and number of hours annually | Stormwater Staff (David Wheeler, Marisa Rorabaugh, Monika Ingalls) attended a total of 50.5 hours of in-person trainings. | Appendix H | Continue to attend virtual and in-person trainings.
6.b (3) | Implement controls for reducing or eliminating the discharge of pollutants from the MS4 | Report number of pet waste bags distributed on an annual basis. | The City distributed 48,000 pet waste bags in 2023. |  | Continue to distribute and report on the number of pet waste bags distributed.
| STPs constructed, upgraded, & maintained | Report number of STPs constructed, upgraded and maintained | In, 2023 the City began construction on the Burlington Country Club project (PB0056) and the Lindenwood project (PB0050), which were then added to our maintenance list. The City maintained all 93 STPs on our list. | Appendix F | In 2024, the City will finish construction on the Kennedy Drive Pond 2 Expansion (PB0041).
| STPs incorpoated into the MS4 | Report on the STPs incorporated into the City's MS4 permit | In 2023, 1 permit was formally incorporated in the City's MS4. The treatment practice covered by this permit was already maintained and operated by the City. | Appendix F | In 2024, the City will finish construction on the Kennedy Drive Pond 2 Expansion (PB0041).
| Inspections performed on fleet vehicles, buildings, garages, parks, open spaces | Report generally on City maintenance | The City has a two full time mechanics that maintain all fleet vehicles, including pickup trucks, street sweepers and vactor trucks. The City has full time maintenance staff to maintain parks and open spaces. |  | The City will continue to maintain its fleet, parks and open spaces.
| Catch basin cleaning | Clean a minimum of 250 storm drains annually and report total volume collected and inspect 350 storm drains each year and report annually. | Cleaned 262 storm drains; collected 54 cubic yards of material from storm drain cleaning. | Appendix I | Continue to clean a minimum of 250 storm drains.
| Street Sweeping | Street sweeping all curbed streets, curbed bike paths, and parking lots with curb that the City owns at least twice per year. The total volume of material collected will be reported annually. | The total volume of material collected from street sweeping was 540 cubic yards. |  | Continue to sweep streets twice per year.
| Leaf/organic waste removal program | Properly dispose of maintenance materials according to City approved procedure | The City was unable to accurately measure leaf material collected from street sweeping in 2023, as CSWD has stopped accepting leaf material for composting. The City continues to work to develop a solution for volume accounting, as well as composting leaves on-site. |  | Look into system to compost leaves on-site.
6.b (4) | Develop and implement procedures for proper disposal of wastes | Properly dispose of maintenance materials according to City approved procedure | The City continues to follow disposal procedure as outlined in Appendix C of the City's approved Stormwater Management Program "Procedure for Handling Material Collected During Street Sweeping, Catch Basin and Stormwater Pipe Cleaning, and Stormwater Pond Maintenance" |  | Continue to properly dispose of maintenance materials according to City approved procedure.
6.c | Prohibit use of phosphorus containing fertilizers on facility operations unless warranted by a soil test; submit copy of test | Soil test submitted with annual report, as applicable. | The City continues to follow the prohibition of use of any phosphorous containing fertilizer on municipally controlled parks and recreational fields, unless warranted by a current soil test or for starting grass on exposed soil. No soil tests were needed in 2023. |  | Continue to submit soil tests with annual report, as applicable.
6.d | Participate in the Agency's Municipal Compliance Assistance Program (or other audit program) for municipal garages |  | The City's last MCAP inspection was June 30, 2016 | Appendix G | The MCAP Program no longer exists
| Other | Calibrate every winter the salt delivery systems | Calibrated salt delivery system on each plow truck. |  | Continue to calibrate salt delivery systems on all plow trucks.

## Additional Reporting
Additional MS4 Reporting Requirements
Annual Review of SWMP completed | No
Results of information collected and analyzed, if not included elsewhere
Notice that permittee is relying on another entity to satisy some of its permit obligations | In order to meet MS4 permit obligations, the City relies on the Regional Stormwater Education Program (RSEP) to meet requirements of Minimum Measure 1 and the Chittenden County Stream Team (CCST) to meet requirements of Minimum Measure 2. South Burlington relies on the Vermont Department of Environmental Conservation (VT DEC) to meet stream flow monitoring requirements found in Section IV.C.1(e)(7) of the MS4 permit.
Estimated funds spent on stormwater management for the fiscal year*
Other information, if applicable
Impaired Waters Response Plan
Impaired Stream | See FRP Implementation Tab
Impairment | i.e. Chloride
Status of implementation
Planned activities for upcoming year
Other information, if applicable
* Optional response.

## NonStructural BMPs
Non Structural BMP Reporting
Complete Table 1 or 2, depending on tracking method used by MS4
Table 1. Area tracking method |  |  |  | Table 2. Measurement of material tracking method | Table 3. Phosphorus Reduction Factor
Sub Area Name (Lake segment, route, etc.) | Burlington Bay Direct Drainage |  | Shelburne Bay | Combined dry weight of material collected (kg) |  | 2/year (spring and fall) | Monthly | Weekly | 4X in the fall
Area of streets swept (acres) | 3.12 |  |  | OR Cubic yards of material collected | Mechanical Broom | 1% | 3% | 5% | 17%
P Load from Streets where sweeping occurs (kg/year) | 2.34 |  |  | Number of sediment samples taken | Vacuum Assisted | 2% | 4% | 8% | 17%
Sweeper Frequency | 2/year (spring and fall) |  |  | Lab where samples were processed | High Efficiency Regenerative Air-Vacuum | 2% | 8% | 10% | 17%
Sweeper Technology | Vacuum Assisted |  |  | Record the average TP result
Year sweeping started | 2008 |  |  | Was a particle size analysis done?
If weekly or monthly, number of months streets are swept |  |  |  | Please attach results from the lab
Phosphorus Credit | 1.6%
Phosphrous Reduction from Street Sweeping (kg/year) | 0.03744 |  |  | **There is currently no approved accounting methodology based on weight or volume of material collected. Should a method be developed, DEC anticipates information like that in Table 2 could be required.
Catch Basin Cleaning
P Load from Streets where catch basin cleaning occurs (kg/year) | 3.6 | 75.64 | 131.69
Phosphorus Credit | 0% | 0% | 0%
Phosphrous Reduction from Catch Basin Cleaning(kg/year)

## FRP Implementation
Flow Restoration Plan Implementation
| Potash Brook | Bartlett Brook | Munroe Brook | Centennial Brook
Summary of actions taken to implement FRP components | The City completed construction on the Lindenwood Drive (PB0050) and Burlington Country Club (PB0056) projects in 2023. The City commenced construction on the Kennedy Drive Pond 2 Expansion (PB0041) in 2023, with final cosmetic finishes and stabilization to be completed in spring 2024. Kennedy Drive Pond 7 Expansion (PB0044) is slated for construction beginning in 2024. The City continued to advance with the design of the Grandview Drive (PB0031 & PB0032), Airport Dive (PB0009), and Logwood (PB0051) projects. The City continued to advance the design for a variety of 3-Acre sites, which include FRP projects covered by expired permit 1-1241, including Park Rd Detention Pond (PB0063), Golf Course Rd South (PB0029), Economou Farm Pond (PB0024), Nicklaus Circle (PB0057), VNCC Pond B (PB0086) and VNCC Pond C (PB0087). The City also commenced design work for the 3-Acre site and FRP projects Eastwood Commons Pond Expansion (PB0022), Technology Park Pond 1 (PB0098), Technology Park Pond Retrofit (PB0076), and Knoll Circle (PB0046). | The City continued with the design of the BBSTS Expansion (BB0004), Horticultural Farm (BB0010 & BB0011), and Irish Farm (BB0012). Final design for BBSTS Expansion (BB0004) was completed in 2023 and construction is anticipated in 2024. Construction of Irish Farm (BB0012) is expected to commence in 2024, contingent upon final design being completed. Coordination with UVM regarding Horticultural Farm (BB0010 & BB0011) is ongoing. The City continued to advance with design for a variety of 3-Acre sites, including FRP projects covered by expired permit 2-0261, including Whatley Road (BB0017), Deerfield Drive 1 (BB0007), Brownell Way (BB0005), Deerfield Drive 2 (BB0008), Windsor Court (BB0018), and Brownell Way-3 (BB0006). | Both projects identified by the City in the Munroe Brook watershed have been constructued. No additional work is required by the City in this watershed. | The City continued to advance with the design for a variety of 3-Acre sites, which includes FRP projects Queesnbury Pond Retrofit (CB0024), Best Western Windjammer Infiltration Basin A (CB0002) and Best Western Windjammer Infiltration Basin B (CB0003).
What is the MS4's overall status in implementing the FRP? | There are an estimated 88 projects remaining to be implemented in the Potash Brook watershed. This is inclusive of all projects either in the design or concept phase. Out of the original 107 projects identified in the FRP, 15 have been built and 3 have been terminated due to infeasiblity. It is difficult to tell how much work remains to be done to meet the City's flow reduction target in the Potash Brook Watershed, as issues with the State's computer that runs BMPDSS has made it impossible to reasses progress in light of the projects that have been deemed infeasible. The FRP in the Potash Brook Watershed requires the implementation of all identified projects to meet the City's target. It is likely that, in addition to the 3 mentioned above, a number of projects that were identified in the FRP will be deemed infeasible. It is imperative that addtional model runs be made, as the City will likely need to identify new project opportunities to meet the flow reduction target. | There are an estimated 14 projects remaining to be implemented in the Bartlett Brook watershed. This is inclusive of all projects either in the design or concept phase. Out of the original 64 projects identified in the FRP, 45 have been built and 2 terminated due to infeasibility. It is difficult to accurately assess how much work remains to be done to meetin the City's flow reduction target in the Bartlett Brook watershed, as issues with the State's computer that runs BMPDSS has made it impossible to reassess progress in light of projects that have been deemed infeasible or substantially differed from original concept. If all FRP projects identified in the Bartlett Brook watershed were implemented, the City would exceed the required flow reduction. However, additional model BMPDSS model runs are needed to determine if the design changes and loss of infeasible projects will impact the City's ability to meet the required flow reduction. | Implementation in the Munroe Brook watershed is complete. No additional work is required by the City in this watershed. | There are an estimated 21 projects remaining to be implemented in the Centennial Brook watershed. This is inclusive of all projects either in the design or concept phase. Out of the original 38 projects identified in the FRP, 12 have been built and 4 have been terminated due to infeasibility. It is difficult to accurately assess how much work remains to be done to meetin the City's flow reduction target in the Centennial Brook watershed, as issues with the State's computer that runs BMPDSS has made it impossible to reassess progress in light of projects that have been deemed infeasible or substantially differed from original concept. The Centennial Brook watershed is in a unique position in that to meet flow reduction targets, more impervious would need to be built. Additional BMPDSS model runs are needed in light of loss of infeasible projects.
Summary of BMP implentation planned for the next calendar year, if any. | Kennedy Drive Pond 7 Expansion (PB0044) construction is scheduled for the 2024 construction season. | Irish Farm (BB0012) and BBSTS Expansion (BB0004) are expected to begin construction in 2024, contingent upon final permitting being completed. The remainder of the projects are scheduled to be constructed through 2032. | No additional BMP implementation is required by the city in the Munroe Brook watershed. | The remainder of the projects are scheduled to be constructed through 2032.
Assessment of ability to meet outstanding schedule items | The City has been able to stay on track with the approved implementation schedule and intends to do so moving forward. However, it is unclear how much work truly remains to be done, as some projects have been deemed infeasible and issues with the State's computer has prevented any new BMPDSS model runs to be completed. Grant and loan funding has helped the City implement the projects that have been completed. This type of financial assistance will be necessary to keep the implementation schedule on track and to assist owners of private property subject to FRP implementation complete projects. Additionally, increased coordination between ANR departments, specifically wetlands and stormwater, would help greatly as we move forward with projects close to wetlands. | The City has been able to stay on track with the approved implementation schedule and intends to do so moving forward. However, it is unclear how much work truly remains to be done, as there have been no additional BMPDSS model runs performed in light of some projects having substantially changed since conception and some projects having been deemed infeasible. Grant and loan funding has helped the City implement the projects that have been completed. This type of financial assistance will be necessary to keep the implementation schedule on track and to assist owners of private property subject to FRP implementation complete projects. Additionally, increased coordination between ANR departments, specifically wetlands and stormwater, would help greatly as we move forward with projects close to wetlands. | Both projects identified by the City in the Munroe Brook watershed have been constructued. No additional work is required by the City in this watershed. | The City has been able to stay on track with the approved implementation schedule and intends to do so moving forward. However, it is unclear how much work truly remains to be done, as some projects have been deemed infeasible and issues with the State's computer has prevented any new BMPDSS model runs to be completed. Grant and CWSRF loan funding has helped the City implement the projects that have been completed. This type of financial assistance will be necessary to keep the implementation schedule on track and to assist owners of private property subject to FRP implementation complete projects. Additionally, increased coordination between ANR departments, specifically wetlands and stormwater, would help greatly as we move forward with projects close to wetlands.
Stream Flow Monitoring
Does your municipality conduct stream flow monitoring? | Yes
Steam Corridor Protection
Ordinance or regulation adopted to protect and regulate development in sw impaired water stream corridors | https://www.southburlingtonvt.gov/departments/planning_and_zoning/regulations_and_planning_documents.php | *Note: the City's land development regulations a frequently updated, therefore a direct link to the document was not provided, but rather a link to where the latest copy of the City's regulations can be found.

## PCP Development
Phophorus Control Plan Development (PCP)
Road Erosion Inventory (REI) | Uploaded to 'Municipal Roads General Permit Implementation Table'
Are there any segments on the MRGP Implementation Table portal that are incomplete? If so, please describe how the data will be completed. | Complete.
Roads and Outlets planned for upgrade in calendar year 2024. | The City does not have any roads planned for upgrade in 2024. The City plans to upgrade four (4) outlets in 2024.
Extent of street sweeping and catch basin cleaning | See 'Non-structural tab'
Extent of stormwater BMP implementation | See 'BMP Tracking Table'
What is the MS4's overall status in implementing the PCP? | The City will meet its required phosphorus reduction from a combination of constructed projects and projects currently in design. Once stormwater practices that are currently indesign are constructed, the City will have met the phosphorus reduction target. The City will exceed its required phosphorus reduction when all other Flow Restoration Plan projects are implemented and eroded outfalls are repaired.
Assessment of the ability to meet outstanding schedule items | The City will be able to meet outstanding scheduled items.
List of '3 acre sites' that have been taken over by the MS4 in the past calendar year. | No 3 acre sites were taken over by the City in 2023.
Has the additional loading from privately owned land associated with the 3-acre sites been addressed in the phosphorus control plan? If not describe the MS4s plan to address the additional target. | Yes - All permits that have been rolled into the City's MS4 permit have been included in the MS4's baseload. In the PCP, the City has also conservatively added to its baseload the acreage from 3-acre permits that it anticipates will be rolled into the City's MS4 in the future. As the City is on track to exceed its required phosphorus reduction once all other Flow Restoration Plan projects are implemented and eroded outfalls are repaired, additional sites that were not accounted for in the FRP will not impact the ability to reach the target.