## MCM Reporting
Minimum Control Measure Reporting
GP Part 6.2 | MCM Requirements | Measurable Goal | Description of how requirement was met | List attachments if applicable | Activities planned for next year | Proposed change in BMP or measurable goal?
MM#1: Public Education and Outreach on Stormwater Impacts
1.c. (1) | Website maintained with locally relevant stormwater information | keep annual budget information current on the webpage and promote website’s existence and use in stormwater utility newsletters. | The stormwater website remained in place in 2023 and is updated as needed to inform the community about utility activities. A page was added in 2023 specific to water quality concerns. Accessible here: https://colchestervt.gov/1837/Stormwater-Utility | N/A | No change | No
1.c (2) | Maintain a program to identify opportunties and provide technical assistance on Low Impact BMPs | Technical Review Committee (TRC) Meetings - Continue to provide TRC reviews for land owners on an as-requested basis and ensure any web links provided are accurate annually | TRC meetings continue to be offered to applicants. Attended by relevant Public Works and Planning/Zoning staff, these were held both online and in person in 2023 with at least 9 meetings held for this purpose. | N/A | No change | No
1.c (3) | Participate in a regional stormwater education strategy or develop an MS4 specific program | RSEP participation and fund support for Rethink Runoff | Colchester continues to participate in RSEP via CCRPC and fund support for ReThink Runoff. | 2023 Invoice, MM1 report | No change | No
| Other | Send one community newsletter to the public annually | Copies of community newsletters sent to all properties in Colchester in 2023 are attached. | Newsletters | No change | No
MM#2: Public Involvement and Participation
2.d | Participate in a regional stormwater public involvement and participation strategy or develop an MS4 specific program | permittee will document on an annual basis the number of participants and/or persons contacted by outreach events and hands-on activities through the Rethink Runoff Stream Team. | Colchester continues to participate in RSEP via CCRPC and fund support for ReThink Runoff. | MM2 Report | No Change | No
Other
MM#3: Illicit Discharge Detection and Elimination
3.a (1) | Develop and maintain a GIS or AutoCAD map of the storm sewers in the regulated MS4 showing all outfalls | The Town has an existing stormwater infrastructure map that shows all outfalls in Colchester. The Town has policies in place to require submittal of as-built data to document changes to the SW system. | The town made significant updates to our GIS data after the completion of a townwide video inspection project of all storm structures and pipes. We recently transitioned to an ArcGIS Online work order system that makes GIS data edits easier to achieve. | N/A | No change | No
3.a (2) | Develop ordinace or policy prohibiting non-stormwater discharges and implement enforcement procedures | Illicit Discharge/Stormwater Ordinance adopted by the Colchester Select Board on July 26, 2005. | This Ordinance is still in place and was not amended during 2023. | N/A | No change | No
3.a (3) | Develop and implement a plan to detect and address non-stormwater discharges | IDDE Plan developed in 2008. | This plan in still in place and was not amended during 2023. | N/A | No change | No
3.a (4) | Inform public on the dangers of illegal discharges | Local business informational brochure and water quality hotline. | These informational documents and programs are still in place, and the WQ hotline is featured on the utility website/in utility newsletters and is monitored at least weekly by DPW staff. | N/A | No change | No
3.a (6) | Status of monitoring activities: |  |  | IDDE report, test results, and invoice | No change | No
| Outfalls Inspected: | 34 | Annual IDDE sampling was conducted as usual in August of 2023. 34 sites were visited with 9 samples taken and processed by Endyne. 0 illicit discharges were detected or addressed during this time. The Town also performed video inspection of approximately 1,800 linear feet of stormwater pipe.
| Number of dry-weather samples taken: | 9
| Feet of storwmater drainage pipe inspected: | 1800
| Discharges Detected: | 0
| Discharges Corrected: | 0
Other
MM#4: Construction Site Stormwater Runoff Control
4.a (1) | Develop and implement procedures to ensure that construction activities undertaken by the MS4 are properly permitted | continue to perform plan review of all projects involving land disturbance as a part of the site plan review process and the issuance of building permits. | Projects involving land disturbance continue to be reviewed through the site plan and building permit processes, with 464 permits issued in 2023. The Town did not undertake any construction projects this year. | Memo from Planning & Zoning regarding # of permits issued.
| Number of permitted MS4 construction projects: | 1 | The Town received approval to construct a new Community Recreation Facility that was properly permitted under both Town (site plan, conditional use, building permit) and State (CGP, SW operational permit) requirements.
4.a (2) | Review existing policies to determine effectiveness, consistency with state standards; Amend for consistency with state standards | Town relies upon the technical specifications within the Public Works Ordinance and the Town’s Stormwater Ordinance as the mechanism to require erosion and sediment controls at construction sites. | Current ordinances are consistent with state standards where applicable. | N/A | No change | No
4.a (3) | Develop and implement ordinance that regulates earth disturbance <1ac | Town’s Stormwater Ordinance (Chapter 18) | This Ordinance is still in place and the relevant section was not amended during 2023. | N/A | No change | No
| Number of projects with <1ac of disturbance subject to MS4 requirements: | 12 | 6 projects were subject to a local EPSC permit in 2023. an example approval is provided. | Approval EPSC | No change | No
Other
MM#5: Post Construction Stormwater Management for New Development and Redevelopment
5.d | Review existing policies to determine effectiveness, consistency with state standards, opportuntities for LID, and opportunties for changes to street and parking requirements; Amend for consistency with state standards | Current regulations are consistent with and as stringent as state requirements. Zoning and technical specifications have been amended to include GSI and LID and will be regularly re-assessed. | This Ordinance is still in place and relevant sections were not amended in 2023. | N/A | No change | No
5.e | Develop and implement procedures to identify projects that disturb >1ac but do not require a state post-construction permit | Projects that create 1/2 acre of new impervious or greater must apply for a building permit and provide a Stormwater Management Plan. |  | N/A | No change | No
| Number of projects >1ac of disturbance <1ac of impervious: | 0 | This Ordinance is still in place and relevant sections were not amended in 2023. There were no projects that fell into this category in 2023. | N/A | No change | No
5.f | Adopt an ordinance or policy that requires projects that disturb >1ac to utilize a combination of structural, non-structural, and low impact BMPs and ensure long-term maintenance | Town’s Public Infrastructure Ordinances, Stormwater Ordinances, Sub-division Regulations and Zoning Ordinances | This Ordinance is still in place and relevant sections were not amended in 2023. There were four projects that had over one acre of disturbance in 2023. | N/A | No change | No
5.g (1) | Develop and implement procedures for inspecting projects subject to the MS4's ordinance | Town’s Zoning Regulations require all ground disturbing activities to obtain a permit, and all permits require inspections by the Town’s Building Inspector for compliance with conditions of approval before the project receives a Certificate of Occupancy. | Inspections to determine compliance with Town regulations are conducted through the Planning & Zoning Office in accordance with regulations; this did not change in 2023. The Town performed 346 inspections in 2023. | Memo from Planning & Zoning regarding # of inspections performed. | No Change | No
| Number of STPs (without state permits) inspected by MS4: | 0 | There were no stormwater systems serving sites with over one acre of disturbance not subject to the Agency's regulations inspected in 2023. | N/A | No change | No
5.g (2) | Develop and implement procedures to ensure that development activities undertaken by the MS4 are properly permitted | Town has adopted Construction Standards Applicable to Land Development, also known as Chapter 14 of the Colchester Code of Ordinances, and technical staff to manage implementation. | This Ordinance is still in place and relevant sections were not amended in 2023. The Town received approval to construct a new Community Recreation Facility that was properly permitted under both Town (site plan, conditional use, building permit) and State (CGP, SW operational permit) requirements. | N/A | No change | No
Other
MM#6: Pollution Prevention and Good Housekeeping for Municipal Operations
6.b (2) | Conduct stormwater training for staff | Town maintenance crews shall receive annual training through the Town’s municipal operations. | Staff provided an onsite training to 11 employees ton April 11, 2023 regarding procedures to minimize discharges of pollutants, municipal operations-related possible sources of contamination, specific requirements associated with compliance with the Towns MS4 permit, and proper waste disposal techniques. A copy of these training materials were submitted in our 2022 Annual Report and have not changed. | N/A | Same /updated presentation to highway crews.
6.b (3) | Implement controls for reducing or eliminating the discharge of pollutants from the MS4 | Implementing snow and ice removal procedures; conducting street sweeping in spring and fall; cleaning catch basins; inspecting stormwater outfalls; drainage ways are maintained; dust is controlled - 1 application per year; EPSC practiced at Public Works maintenance yard | All procedures still in place. | Memo from Operations | No change | No
| STPs constructed, upgraded, & maintained |  | List in BMP tracking table
| STPs incorpoated into the MS4 |  | List in BMP tracking table
| Inspections performed on fleet vehicles, buildings, garages, parks, open spaces | Inspection performed as part of training. | No needed maintenance.
| Catch basin cleaning |  | Complete 'Non Structural Tab'
| Street Sweeping |  | Complete 'Non Structural Tab'
| Leaf/organic waste removal program |  | Complete 'Non Structural Tab'
6.b (4) | Develop and implement procedures for proper disposal of wastes | On-site wastewater for parks - inspected and pumped every 2 to 3 years; solid waste collected from parks daily by maintenance crews; proper hazardous waste management at Public Works facility. | All procedures still in place. | N/A | No change | No
6.c | Prohibit use of phosphorus containing fertilizers on facility operations unless warranted by a soil test; submit copy of test | Reduce use and only use as needed and require a soil test | No fertilizers used by municipal staff for facility operations in 2023. | N/A | No change | No
6.d | Participate in the Agency's Municipal Compliance Assistance Program (or other audit program) for municipal garages | Continue to work with the MCAP program | Per our materials handling policy we tested the materials received from basin cleaning to ensure suitability for other uses. Attached is documentation of that test and result. | Invoice and test results from endyne | No change | No
Other

## Additional Reporting
Additional MS4 Reporting Requirements
Annual Review of SWMP completed | Yes
Results of information collected and analyzed, if not included elsewhere
Notice that permittee is relying on another entity to satisy some of its permit obligations | CCRPC to complete MM1 & 2, DEC for Flow Monitoring
Estimated funds spent on stormwater management for the fiscal year* | 850000
Other information, if applicable
Impaired Waters Response Plan
Impaired Stream | Sunnyside Brook
Impairment | Chloride
Status of implementation | Response Plan was submitted with 2023 MS4 renewal package on 3-26-2024.
Planned activities for upcoming year | Ensure compliance with Plan requirements.
Other information, if applicable
* Optional response.

## NonStructural BMPs
Non Structural BMP Reporting
Complete Table 1 or 2, depending on tracking method used by MS4
Table 1. Area tracking method |  |  |  | Table 2. Measurement of material tracking method |  | Table 3. Phosphorus Reduction Factor
Sub Area Name (Lake segment, route, etc.) |  |  |  | Combined dry weight of material collected (kg) |  |  | 2/year (spring and fall) | Monthly | Weekly | 4X in the fall
Area of streets swept (acres) |  |  |  | OR Cubic yards of material collected | 157 | Mechanical Broom | 1% | 3% | 5% | 17%
P Load from Streets where sweeping occurs (kg/year) | 20 |  |  | Number of sediment samples taken | 2 | Vacuum Assisted | 2% | 4% | 8% | 17%
Sweeper Frequency | 4X in the fall |  |  | Lab where samples were processed |  | High Efficiency Regenerative Air-Vacuum | 2% | 8% | 10% | 17%
Sweeper Technology | Mechanical Broom |  |  | Record the average TP result
Year sweeping started | 2008 |  |  | Was a particle size analysis done?
If weekly or monthly, number of months streets are swept | 6 |  |  | Please attach results from the lab
Phosphorus Credit | 6.8%
Phosphrous Reduction from Street Sweeping (kg/year) | 1.36 |  |  | **There is currently no approved accounting methodology based on weight or volume of material collected. Should a method be developed, DEC anticipates information like that in Table 2 could be required.
Catch Basin Cleaning
P Load from Streets where catch basin cleaning occurs (kg/year)
Phosphorus Credit | 2% | 2% | 2%
Phosphrous Reduction from Catch Basin Cleaning(kg/year)

## FRP Implementation
Flow Restoration Plan Implementation
| Morehouse Brook NOTE: Colchester is collaborating with Winooski on Morehouse Brook FRP implementation efforts. Winooski is managing the implementation and Colchester is providing financial support for our portion of required improvements. The following updates were provided by Winooski and are copied below, as is, for consistency of reporting. | Sunderland Brook
Summary of actions taken to implement FRP components | In 2019, City of Winooski (with cost sharing contribution from Town of Colchester) completed construction of several BMPs on Pinegrove Terrace (PGT) and adopted an expired stormwater permit (1-0576) from the PGT HOA for coverage under Winooski's MS4 permit. | N/A
What is the MS4's overall status in implementing the FRP? | PGT Pond Upgrade (WIN-3+4 in the Morehouse FRP; WIN001 in Winooski's 2021 BMP Tracking Table) and four Bioretention Bumpouts on PGT (WIN002-WIN005 in the Tracking Table) were installed in 2019. The City is not aware of any new unregulated impervious development within the Morehouse watershed. | N/A
Summary of BMP implentation planned for the next calendar year, if any. | Remaining BMPs for implementation include the Landry Park Sand Filter (WIN-5/6 in the Morehouse FRP; WIN011 in Winooski's 2021 BMP Tracking Table) and Brisson Ct / Cedar St Bioretention (WIN-1 in the FRP, WIN012 in the Tracking Table). These projects are planned only; preliminary engineering planned for 2022-2024, with full design and construction to proceed sometime thereafter. These projects are also identified in Winooski's PCP. | N/A
Assessment of ability to meet outstanding schedule items | Winooski foresees no issue with completing implementation of remaining items as required by 2032. | N/A
Stream Flow Monitoring
Does your municipality conduct stream flow monitoring? | No
Steam Corridor Protection
Ordinance or regulation adopted to protect and regulate development in sw impaired water stream corridors | https://clerkshq.com/Colchester-vt

## PCP Development
Phophorus Control Plan Development (PCP)
Road Erosion Inventory (REI) | Uploaded to 'Municipal Roads General Permit Implementation Table'
Are there any segments on the MRGP Implementation Table portal that are incomplete? If so, please describe how the data will be completed. | No
Roads and Outlets planned for upgrade in calendar year 2023. | The Town completed work on Macrae Rd using Grants in Aid Funds in regards to MRGP implementation in 2023.
Extent of street sweeping and catch basin cleaning | See 'Non-structural tab'
Extent of stormwater BMP implementation | See 'BMP Tracking Table'
What is the MS4's overall status in implementing the PCP? | On track. The updated PCP was submitted in March of 2024 and includes a comprehensive accounting of what projects have been implemented, what projects are planned for compliance, and their implementation timeline, broken out by lake segment.
Assessment of the ability to meet outstanding schedule items | No concerns at this point.
List of '3 acre sites' that have been taken over by the MS4 in the past calendar year. | See "Permit Incorporation Form" from November 2023 submittal for additional information. Sites include Creekside Park, Hollow Creek, Whispering Pines, Carriage Hill, Valleyfield, Blakely Woods, and Bay Creek. The Town is also pursuing incorporation of the Meadows Indutrail Park 3-acre permit but those discussions with proeprty owners have not yet resulted in us being able to meet the requirement of "having secured legal responsibilty for the site" by the time of the MS4 renewal/annual workbook submittal.
Has the additional loading from privately owned land associated with the 3-acre sites been addressed in the phosphorus control plan? If not describe the MS4s plan to address the additional target. | Yes. A section in the updated PCP describes which sites were taken over and the resulting impact on reduction targets.