## MCM Reporting
Minimum Control Measure Reporting
GP Part 6.2 | MCM Requirements | Measurable Goal | Description of how requirement was met | List attachments if applicable | Activities planned for next year | Proposed change in BMP or measurable goal?
MM#1: Public Education and Outreach on Stormwater Impacts
1.c. (1) | Website maintained with locally relevant stormwater information | Maintain basic stormwater information with links; Annual number of visits to the website | https://www.burlingtonvt.gov/DPW/Stormwater-Management | NA | NA | No
1.c (2) | Maintain a program to identify opportunties and provide technical assistance on Low Impact BMPs | Links provided on website to non-profits and government resource sites | With the assistance of a hired contractor, Burlington has implemtned the BLUE BTV Program providing incentives to residential properties which implement recommended stormwater practices. Main Site: https://www.burlingtonvt.gov/water/BLUErequest Story Map of Progress: https://storymaps.arcgis.com/stories/f17f3e4f2661430eb3158a2d6ed2528c#n-krNH4P FY23 Report: https://www.uvm.edu/seagrant/sites/default/files/files/publication/BLUE%20BTV%20Year%201%20Report.pdf | See provied links for more information. | Continue Year 3 of the Residential Stormwater Incentive Program | No
1.c (3) | Participate in a regional stormwater education strategy or develop an MS4 specific program | Participation; financial support; survey of residents every 5 years; annual number of visits to website www.rethinkrunoff.org | Paid annual dues for http://rethinkrunoff.org/ . See Attachment for MCM#1 for additional details. | Attachment for MCM #1 | Continuing support of http://rethinkrunoff.org/ | No
| Other | Provide regular updates on social media accounts; track "likes," "follows," and general engagement statistics | The Stormwater Program works hand in hand with the Public Information Manager to keep the public up-to-date on all things Stormwater. The following outreach platforms have all been used by the Stormwater Program during this past year. Media and Public Engagement Website (https://www.burlingtonvt.gov/dpw/engagement) - Instagram (@btv_dpw) - Facebook (https://www.facebook.com/BTVDPW/) - Front Porch Forum (various officials) | NA | NA | No
MM#2: Public Involvement and Participation
2.d | Participate in a regional stormwater public involvement and participation strategy or develop an MS4 specific program | Participation; financial support; number of participants and/or persons contacted | See Stream Team attachment for MCM #2 | Attachment for MCM #2 | Continuing support of the Stream Team efforts | No
| Other | Annual number of new sign-ups | See Stream Team attachment for MCM #2 | Attachment for MCM #2 | Continuing support of the Stream Team efforts | No
MM#3: Illicit Discharge Detection and Elimination
3.a (1) | Develop and maintain a GIS or AutoCAD map of the storm sewers in the regulated MS4 showing all outfalls | Maintain updated map, available on BSP website; Inventory system using CCTV and report on % of system filmed | The following web map (https://maps.burlingtonvt.gov/portal/home/webmap/viewer.html?webmap=813572bb8ebd490a9343c3b4bb2df58f) [access limited to those with approved accounts] is maintained continuously by DPW's Water Resources Infrastructure Asset Manager. Each time a DPW Water resources team member inspects a piece of infrastrucure including catch basins, combined sewer pipes, and outfalls any anomalies are reported to the Asset Manager and updated immediately. | NA | Limited staffing has continued to limit IDDE inspections. In late-2023 the Stormwater Program received BOF/CC approval to hire a Stormwater Field Specialist, which will double the current staffing from one full time Stormwater staffer to two. This staffer will be charged with revitalising the IDDE program within Burlington. | No
3.a (2) | Develop ordinace or policy prohibiting non-stormwater discharges and implement enforcement procedures | Report any enforcement actions taken under City's Chapter 26 Ordinance | Continue reporting any applicable illicit discharges to the State. |  |  | No
3.a (3) | Develop and implement a plan to detect and address non-stormwater discharges | IDDE Standard Operating Procedure | Phase 1 of an advanced IDDE monitoring effort was performed in 2018. Proposals for Phase 2 were received in January of 2020, however due to the pandemic coordination efforts ceased in March of that year. Once increased staffing and/or a contractor is hired, Phase 2 is anticipated to take place. The result of these phased IDDE efforts performed with the help of outside consultants will be two fold including 1) advanced IDDE efforts performed in specific areas to address known unknowns and 2) develope a more robust internal IDDE monitoring SOP. |  | Onboarding of new Stormwater hire will expand City staffing resources to perform proactive IDDE investigations. Phase 2 of Advanced IDDE Effort Possible Starte 2024/2025. | No
3.a (4) | Inform public on the dangers of illegal discharges | NA |  |  | Same as 2023 | No
3.a (6) | Status of monitoring activities: | Notify the Secretary as soon as possible following confirmation of an illicit discharge; Provide results of IDDE assessments in annual report |  |  | Same as 2023 | No
| Outfalls Inspected: |  | Due to ongoing staffing shortages and emergency response efforts associated with the July storms City Stormwater staff were unable to perform official outfall inspections. However, the following list of outfalls were visited and unofficially inspected during 2023. TO-0126, TO-0128, TO-0129, TO-0131, TO-0130,TO-0127,TO-0121, TO-119, TO-0112, TO-0104, TO-0102, TO-0098, TO-0099, TO-0097, TO-0089 (resulting in the discovery of an Illicit Discharge), TO-0080, TO-0081, TO-0082, TO-0058, TO-0044, TO-0003, TO-0013, TO-0016, TO-0134, TO-0137, TO-0138, TO-0140, TO-0143, TO-0149 (undiscoverable), TO-0267, TO-0144, TO-0215, TO-0217,TO-0223, TO-0226. |  | An RFP For contracted Outfall Assment Contractors was released in early 2021. This effort is still underway in 2023. | No
| Number of dry-weather samples taken: |  |  |  | Pending increased staffing and/or contractor procurement | No
| Feet of storwmater drainage pipe inspected: | See Description | No proactive IDDE pipe inspections were performed in 2021. All inspections were in preperation for future constrtuction projects, in response to improperly functioning infrastructure, or in response to a known discharge.
| Discharges Detected: | 2 | TO-0089 and TI-1084 | See Attachment for MCM#3 | Onboarding of new Stormwater hire will expand City staffing resources to perform proactive IDDE investigations. Phase 2 of Advanced IDDE Effort Possible Starte 2024/2025. | No
| Discharges Corrected: | 2 | TI-1084 (Vac truck cleaned the catch basin) | See Attachment for MCM#3 containing a full report of the IDDE effort for TO-0089. Next steps include involving the State of Vermont to review the private septic systen suspected of being the culprit for this IDDE |  | No
Other
MM#4: Construction Site Stormwater Runoff Control
4.a (1) | Develop and implement procedures to ensure that construction activities undertaken by the MS4 are properly permitted | Article III of Chapter 26 Ordinance | Article III of Chapter 26 Ordinance regulates development and re-development for proper stormwater management for both public and private projects. | See relevant portions of Attachment for MCM #4 from the 2021 Annual Report | Same as 2023 | No
| Number of permitted MS4 construction projects: |  | 91 Projects reviewed for compliance with CH26 EPSC measures. 16 Projects received Residential PCSW Permits. 8 Projects began PCSW review in 2022. |  | Same as 2023 | No
4.a (2) | Review existing policies to determine effectiveness, consistency with state standards; Amend for consistency with state standards | exceeds state standards | CH 26 regulations continue to exceed state standards | See relevant portions of Attachment for MCM #4 from the 2021 Annual Report | Same as 2023 | No
4.a (3) | Develop and implement ordinance that regulates earth distrubance <1ac | Article III of Chapter 26 Ordinance; | City permitting is now digital and can be found at https://burlingtonvt.viewpointcloud.com/ . The direct link to the EPSC permit is provided below. https://burlingtonvt.viewpointcloud.com/categories/1091/record-types/6485 |  | Updated CH26 Forms via the initial launch of OpenGov | No
| Number of projects with <1ac of disturbance subject to MS4 requirements: | List of projects | The Stormwater Program reviewed 96 EPSC permits and 15 PCSW permits. | See relevant portions of Attachment for MCM #4 from the 2021 Annual Report | Same as 2023 | No
Other
MM#5: Post Construction Stormwater Management for New Development and Redevelopment
5.d | Review existing policies to determine effectiveness, consistency with state standards, opportuntities for LID, and opportunties for changes to street and parking requirements; Amend for consistency with state standards | Article III of Chapter 26 Ordinance, exceeds state standards | Policy exceeds state standards. Additionaly, narrow Streets policy allows for the implementation of stormwater retrofit "bumpouts" within roadways as long as the curb-to-curb width remains equal too or greater than 14'. | See relevant portions of Attachment for MCM #5 from the 2021 Annual Report | Same as 2023 | No
5.e | Develop and implement procedures to identify projects that disturb >1ac but do not require a state post-construction permit | Number of applications reviewed | All projects disturbing >1ac required a State SW Permit. |  | Same as 2023 | No
| Number of projects >1ac of disturbance <1ac of impervious: | Article III of Chapter 26 Ordinance | Article III of Chapter 26 Ordinance | See relevant portions of Attachment for MCM #5 from the 2021 Annual Report | Same as 2023 | No
5.f | Adopt an ordinance or policy that requires projects that disturb >1ac to utilize a combination of structural, non-structural, and low impact BMPs and ensure long-term maintenance | number of post-construction inspections completed | 0 UCO Post-Construction Inspections Performed |  | Process improvements anticipated | No
5.g (1) | Develop and implement procedures for inspecting projects subject to the MS4's ordinance |  | 0 UCO Post-Construction Inspections Performed (Private Property). Internal (public) STP inspections are currently not recorded. However all our sub-surface storage systems are inspected annually, as are our surface bioretention bumpouts. |  | Process improvements anticipated | No
| Number of STPs (without state permits) inspected by MS4: | Article III of Chapter 26 Ordinance | Article III of Chapter 26 Ordinance | See relevant portions of Attachment for MCM #5 from the 2021 Annual Report | Same as 2023 | No
5.g (2) | Develop and implement procedures to ensure that development activities undertaken by the MS4 are properly permitted | Update the Chapter 26 Credit Manual | No credit applications requested in calendar year 2023. |  | Same as 2023 | No
| Other | Number of people applying for incentives annually | In calendar year 2023 the City continued the second year rof theResidential Incentive Program (Blue BTV) which provided incentives to private property owners to implemnt residential stormwater controls. |  | Updated Residential Incentive Program launched and first year completed. | No
MM#6: Pollution Prevention and Good Housekeeping for Municipal Operations
6.b (2) | Conduct stormwater training for staff |  | None performed in 2023, EPSC training planned for 2024 |  |  | No
6.b (3) | Implement controls for reducing or eliminating the discharge of pollutants from the MS4 |  |  |  | Same as 2023 | No
| STPs constructed, upgraded, & maintained |  | In 2023 the City constructed 1 bioretention system. The City’s 40 bioretention systems surficial components are now maintained by the Department of Parks, Recreation, and Waterfront with the subsurface components maintained by the Stormwater Program. Two porous asphalt parking lots and porous pavers along St. Paul and within City Hall Park were cleaned using specialized porous cleaning equipment. | See relevant portions of Attachment for MCM #6 from the 2021 Annual Report | Same as 2023 | No
| STPs incorpoated into the MS4 |  | No STP's formally incorporated into the MS4, however all STP's listed above are owned and managed by the City of Burlington and exist either in the City's ROW and/or on municipal properties. |  | Two Additional bioretention systems are anticipated to be constructed as part of a traffic calming effort in the Old North End. | No
| Inspections performed on fleet vehicles, buildings, garages, parks, open spaces | Functioning Equipment | The City of Burlington has a dedicated Fleet Maintenance team which inspects and maintains all stormwater machinery. |  | Same as 2023 | No
| Catch basin cleaning | # Cleaned | 1,191 Catch Basins Cleaned |  | Same as 2023 | No
| Street Sweeping | # Miles Swept | 2419 |  | Same as 2023 | No
| Leaf/organic waste removal program | Yardage Collected | City Staff reached out to CSWD for confirmation of this value and has not heard back as of 4/1/2024 |  | Same as 2023 | No
6.b (4) | Develop and implement procedures for proper disposal of wastes | Yards | 2,231 yds Street Sweeping Debris Collected |  | Same as 2023 | No
6.c | Prohibit use of phosphorus containing fertilizers on facility operations unless warranted by a soil test; submit copy of test |  | See Procedure for Handling Material Collected During Street Sweeping, Catch Basin and Stormwater Pipe Cleaning in Attachment for MCM#6 | See relevant portions of Attachment for MCM #6 from the 2021 Annual Report | Same as 2023 | No
6.d | Participate in the Agency's Municipal Compliance Assistance Program (or other audit program) for municipal garages |  | See Pesticide/Herbicide ordinance in Attachment for MCM#6 | See relevant portions of Attachment for MCM #6 from the 2021 Annual Report | Same as 2023 | No
| Other | Document audit once per permit cycle | Last known inspection was in 2008. The City is willing to schedule another inspection with the State at their convenience. |  | Same as 2023 | No

## Additional Reporting
Additional MS4 Reporting Requirements
Annual Review of SWMP completed | Yes
Results of information collected and analyzed, if not included elsewhere
Notice that permittee is relying on another entity to satisy some of its permit obligations | CCRPC is responsible for MCM#1 and MCM#2
Estimated funds spent on stormwater management for the fiscal year* | Total expenses for calendar year 2023 not including debt service or capital leases = $1,961,208.87
Other information, if applicable
Impaired Waters Response Plan
Impaired Stream | See Engelsby, Potash, and Centennial Brook FRP's on the City of Burlington Website
Impairment | Stormwater
Status of implementation | In Progress
Planned activities for upcoming year | UVM Main Pond PPP Discussions commenced in 2023, the Champlain Parkway will be implementing stormwater practices to achieve compliance within Englesby Brook
Other information, if applicable
* Optional response.

## NonStructural BMPs
Non Structural BMP Reporting
Complete Table 1 or 2, depending on tracking method used by MS4
Table 1. Area tracking method |  |  |  | Table 2. Measurement of material tracking method |  | Table 3. Phosphorus Reduction Factor
Sub Area Name (Lake segment, route, etc.) |  |  |  | Combined dry weight of material collected (kg) |  |  | 2/year (spring and fall) | Monthly | Weekly | 4X in the fall
Area of streets swept (acres) |  |  |  | OR Cubic yards of material collected | 2,231 yards of street sweeping material collected | Mechanical Broom | 1% | 3% | 5% | 17%
P Load from Streets where sweeping occurs (kg/year) | 20 |  |  | Number of sediment samples taken | 2 (EPA 8260C low and high for Grit Pile Testing) | Vacuum Assisted | 2% | 4% | 8% | 17%
Sweeper Frequency | 4X in the fall |  |  | Lab where samples were processed | Endyne | High Efficiency Regenerative Air-Vacuum | 2% | 8% | 10% | 17%
Sweeper Technology | Mechanical Broom |  |  | Record the average TP result | NA
Year sweeping started | 2008 |  |  | Was a particle size analysis done? | NA
If weekly or monthly, number of months streets are swept | 6 |  |  | Please attach results from the lab
Phosphorus Credit | 6.8%
Phosphrous Reduction from Street Sweeping (kg/year) | 1.36 |  |  | **There is currently no approved accounting methodology based on weight or volume of material collected. Should a method be developed, DEC anticipates information like that in Table 2 could be required.
Catch Basin Cleaning
P Load from Streets where catch basin cleaning occurs (kg/year)
Phosphorus Credit | 2% | 2% | 2%
Phosphrous Reduction from Catch Basin Cleaning(kg/year)

## FRP Implementation
Flow Restoration Plan Implementation
| Englesby Brook | Potash Brook | Centennial Brook
Summary of actions taken to implement FRP components | 08 Pond update to CMAC system, various Champlain Parkway related SW improvements addressing the impairment to Englesby. | A Public Private Partnership between the City of Burlington, Pomerleau Real Estate, and CHT is on going having received design funds via a Watershed United Vermont and was was awarded federal dollars for implementation (2022 ARPA - 3 Acre - Public-Private Partnership Project Construction – Burlington Champlain Housing Trust- Pomerleau, Grant # 06140-ARPA-CWB-03). This project is ongoing with final design anticipated in 2024 with implementation taking place prior to 2025. | NA
What is the MS4's overall status in implementing the FRP? | In progress | In progress | In progress
Summary of BMP implentation planned for the next calendar year, if any. | Continued Champlain Parkway project implementation, M19 (Pine St. Counseling Center) is submitting permits in 2023 which will include meeting the requriements laid out for M19 in the Englesby FRP | PPP above. MOU executed in 2024 with project anticipated to be awarded in 2024. | Kick-off meeting for UVM Main Pond updates started in 2023. Follow-up pendingin Spring of 2024.
Assessment of ability to meet outstanding schedule items
Stream Flow Monitoring
Does your municipality conduct stream flow monitoring? | Yes, since the State stopped requiring monitoring and providing financial assistance the City now monitors solely Englesby brook for flow.
Steam Corridor Protection
Ordinance or regulation adopted to protect and regulate development in sw impaired water stream corridors | link to relevant municipal ordinance

## PCP Development
Phophorus Control Plan Development (PCP)
Road Erosion Inventory (REI) | Implementation Table (Portal) Link provided. | https://anrweb.vt.gov/DEC/IWIS/MRGPReportViewer.aspx?ViewParms=True&Report=Portal
Are there any segments on the MRGP Implementation Table portal that are incomplete? If so, please describe how the data will be completed.
Roads and Outlets planned for upgrade in calendar year 2023. | If these have not been identified in the Implementation Table, to the best of your ability, list them here.
Extent of street sweeping and catch basin cleaning | See 'Non-structural tab'
Extent of stormwater BMP implementation | See 'BMP Tracking Table'
What is the MS4's overall status in implementing the PCP?
Assessment of the ability to meet outstanding schedule items
List of '3 acre sites' that have been taken over by the MS4 in the past calendar year.
Has the additional loading from privately owned land associated with the 3-acre sites been addressed in the phosphorus control plan? If not describe the MS4s plan to address the additional target.