EPA’s Volunteer Monitor’s Guide to Quality Assurance Project Plans

Element 1.

Long-Term

Five Year: 2018 – 2022

QUALITY CONTROL / QUALITY ASSURANCE PROJECT PLAN

LAY MONITORING PROGRAM FOR LAKE CHAMPLAIN

Prepared by

Mark Mitchell

Vermont Agency of Natural Resources

Department of Environmental Conservation

Watershed Management Division

1 National Life Drive, Main 2

Montpelier, VT 05620-3522

(802) 490-6129

Mark.Mitchell@Vermont.gov

May 2018

________________________________________________________________

Mark Mitchell, VTDEC Project Manager                           Date

________________________________________________________________

Jeanne Vorhees, USEPA Program Manager 	Date

________________________________________________________________

Steve DiMattei, USEPA QA/QC Officer                      	Date

________________________________________________________________

Dan Needham, VTDEC Laboratory Supervisor	Date

Element 2.

Table of Contents

List of Tables and Figures

Figure 1. Organizational Chart	1

Table 1. Timeline	2

Table 2. Lake Champlain Lay Monitoring Stations	3

Table 3. QA Objectives for Precision, Accuracy, and Quantitation Limit	4

Table 4. Sampling Method and Quantity Requirements	6

Table 5. Parameter Table	6

List of Elements

Element 3. Distribution List	1

Element 4. Project Task Organization	1

Element 5. Problem Definition/Background	1

Element 6. Project/Task Description	2

Element 7. Data Quality Objectives for Measurement Data	4

Element 8. Training Requirements/ Certification	5

Element 9. Documentation and Records	5

Element 10. Sampling Process Design	5

Element 11. Sampling Methods Requirements	6

Element 12. Sampling Handling and Custody Requirements	6

Element 13. Analytical Methods Requirements	6

Element 14. Quality Control Requirements	7

Element 15. Instrument/Equipment Testing, Inspection, and Maintenance Requirements.	8

Element 16. Instrument Calibration and Frequency	8

Element 17. Inspection and Acceptance Requirement for Supplies	8

Element 18. Data Acquisition Requirements	8

Element 19. Data Management	8

Element 20. Assessments and Response Actions	9

Element 21. Reports	9

Element 22. Data Review, Validation and Verification Requirements	9

Element 23. Validation and Verification Methods	9

Element 24. Reconciliation with Data Quality Objectives	9

References 	10

Appendices

Appendix A. Lake Names and Stations	11

Element 3. Distribution List

Mark Mitchell, Project Manager, VTDEC-Watershed Management Division, 1 National Life Drive, Main 2, Montpelier, VT 05620-3522

Dan Needham, Laboratory Supervisor, VTDEC Laboratory, University of Vermont, 105 Carrigan Drive, Hills Agriculture Science Building, Burlington, VT 05405

Jeanne Vorhees, USEPA New England, 5 Post office Square – Suite 100 Mail Stop, OEP05-2,, Boston, MA 029109-3912

Steve DiMattei, USEPA New England, 11 Technology Drive, North Chelmsford, MA 01863-2431

Element 4. Project/Task Organization

Figure 1. Organizational Chart

Project Manager, QA/QC Officer Mark Mitchell responsible for all components of monitoring program

|  |  | QC Leader LMP Summer Assistant – supports the Project Manager with field sampling and data management |  | Laboratory Supervisor Dan Needham oversees all laboratory staff and analysis, including QA/QC |  |  |
| --- | --- | --- | --- | --- | --- | --- |

|  |  | Lay Monitors responsible for collecting and storing lake samples |  |
| --- | --- | --- | --- |

The primary data users are the State DEC, lake associations, and citizen watershed groups.

Element 5. Problem/Definition/Background

General Description

This project is a continuation of the water quality monitoring on Lake Champlain that has been conducted under the Vermont Lay Monitoring Program (LMP) since 1979.  Under the LMP, citizen volunteers are trained to measure water clarity and to collect water samples for chlorophyll-a and total phosphorus analysis.  Through the use of volunteers, essential baseline water quality data is collected, and lake residents and users are better informed regarding lake biology and lake water quality protection.

Project Objectives

The principal objectives of this project are: (1) to collect water quality data and incorporate it into the long-term eutrophication monitoring database started in 1979, (2) to use the data for water quality assessment and management decision-making, and to track progress toward compliance with phosphorus criteria adopted in 1991 as Lake Champlain management objectives, and (3) to educate and involve lake users in lake protection.

Element 6. Project/ Task Description

Sampling

Sampling is designed to monitor trophic state parameters.  Lake Champlain is known to have suffered declines in water quality due to accelerated eutrophication in some regions.  The program, therefore, measures nutrient concentration and primary productivity.  Although sample collection has occurred at 42 different stations since the beginning of the program in 1979, today the program only uses 37 of these stations as these are located throughout the lake and best represent the broad water quality range that exists in Lake Champlain.

Sampling Parameters

Each year the monitored stations on Lake Champlain (Table 1) are sampled weekly from Memorial Day through Labor Day for the following:

- Secchi disk transparency reading

- Chlorophyll-a concentration samples

- Total phosphorus concentration sample

A hose sampling method is used for lake stations deeper than four meters, while sub-surface grab samples are taken at shallower stations.  The sampling procedure is repeated to collect two

chlorophyll-a samples, therefore all chlorophyll-a samples are taken in duplicate at each station and are analyzed separately.  Chlorophyll-a water samples are filtered at a lakeside site.  Filters are then frozen and stored until pickup by program staff.  Total phosphorus water samples are collected in duplicate at least one time during the summer. Monitors take their duplicates during the LMP staff field visits with the monitors.  Also at this time, program staff members take an extra phosphorus sample for laboratory analysis of spiked samples (part of the internal lab QA/QC plan).  All phosphorus samples are stored in glass test tubes.  Program staff transport samples bi-weekly to the DEC Laboratory, currently housed on the University of Vermont campus in Burlington, for processing.  (See Appendix A, Vermont Department of Environmental Conservation, Vermont Lay Monitoring Program Manual, 2000.)

Timeline

Table 1. Timeline

| Date | Task |
| --- | --- |
| May – June | Monitor training |
| June – September | Sample collection |
| June – August | Monitor quality checks |
| December | All lab analyses completed and submitted to Project Manager |
| January | Data entry into project database |
| March | Final project report |

Table 2. Lake Champlain Lay Monitoring Stations

| Station | Latitude (deg min) | Longitude (deg min) | Total Depth (m) |
| --- | --- | --- | --- |
| 01 | 43 34.26 | 73 25.57 | 3 |
| 02 | 43 51.21 | 73 22.58 | 3 |
| 03 | 43 57.06 | 73 24.28 | 3 |
| 04 | 44 11.03 | 73 22.52 | 53 |
| 05 | 44 16.06 | 73 18.44 | 107 |
| 06 | 44 25.33 | 73 13.55 | 22 |
| 07 | 44 27.59 | 73 16.38 | 40 |
| 08 | 44 28.10 | 73 22.34 | 50 |
| 09 | 44 32.46 | 73 19.39 | 10 |
| 10 | 44 34.55 | 73 16.52 | 32 |
| 11 | 44 33.54 | 73 12.30 | 23 |
| 12 | 44 40.19 | 73 14.01 | 30 |
| 13 | 44 40.48 | 73 25.00 | 10 |
| 14 | 44 45.22 | 73 22.15 | 14 |
| 15 | 44 45.18 | 73 18.40 | 4.5 |
| 16 | 44 45.30 | 73 13.16 | 27 |
| 17 | 44 47.07 | 73 09.44 | 6 |
| 18 | 44 51.44 | 73 12.55 | 15 |
| 19 | 44 56.54 | 73 20.24 | 6 |
| 20 | 44 00.48 | 73 10.26 | 4 |
| 21 | 44 39.53 | 73 18.12 | 9 |
| 22 | 44 55.04 | 73 11.11 | 8 |
| 23 | 44 53.09 | 73 16.28 | 3.5 |
| 24 | 44 00.01 | 73 07.33 | 3 |
| 25 | 44 50.12 | 73 18.06 | 4.5 |
| 26 | 44 13.18 | 73 19.32 | 2 |
| 29 | 44 50.23 | 73 17.48 | 7.5 |
| 30 | 44 58.33 | 73 12.54 | 4.5 |
| 31 | 44 38.16 | 73 15.17 | 7.5 |
| 32 | 44 38.32 | 73 22.56 | 58 |
| 33 | 44 28.49 | 73 13.90 | 15 |
| 34 | 44 07.34 | 73 24.46 | 45 |
| 35 | 44 39.40 | 73 24.46 | 6 |
| 36 | 43 34.91 | 73 25.33 | 6 |
| 37 | 44 50.74 | 73 18.67 | 15 |
| 38 | 44 15.78 | 73 17.22 | 8 |
| 39 | 44 16.02 | 73 17.94 | 7 |
| 40 | 44 29.19 | 73 14.37 | 12 |
| 41 | 44 25.46 | 73 16.43 | 68 |
| 42 | 44 00.38 | 73 24.38 | 4 |

Note: Highlighted stations were sampled through the LMP in 2017 and/or are expected to be sampled in 2018. (http://dec.vermont.gov/watershed/lakes-ponds/monitor/lay-monitoring).

Element 7.	Data Quality Objectives for Measurement Data

Quantitative QA Objectives

Lab QA Protocol

Table 3. QA Objectives for Precision, Accuracy, and Quantitation Limit

| Parameter | Sample Matrix | Practical Quantitation Limit (PQL)a | Estimated Accuracy (%Recovery)b | Estimated Precision (RPD)c | Lab RPD |
| --- | --- | --- | --- | --- | --- |
| TP | Water | 5.0 ug/l | 85-115% | 14 | 15d |
| Chlorophyll-a | Water | 0.5 ug/l | - | 17 | 10 |
| Secchi Disk | Water | n/a | n/a | 2.5 | n/a |

a 	PQL is the minimum reported value.

b 	Section 5.0, Vermont Department of Environmental Conservation Laboratory QA Plan, 2007.

c 	Estimated from average relative percent difference of Lay Monitor field duplicates.

d	RPD for phosphorus calculated from instrument duplicates.

Qualitative QA Objectives

Field QA Protocol

Program staff will accompany each monitor on one normal sampling day and observe monitor technique for error.  At this time the sampling procedure is replicated and duplicates are taken by the monitor.  An approximate total of 10% of the field samples will be replicated to validate the accuracy of lay monitoring.  Monitors are asked to collect a minimum of nine samples (not including the duplicates) during June, July and August, which is approximately 64% of the maximum number of weekly samples possible to collect during these three summer months.  A minimum of eight samples is required to calculate a summer mean for the Vermont Lay Monitoring Program (Vermont Lay Monitoring Field Method Manual, 2000).

Completeness: The weekly sampling frequency allows for adequate characterization of productivity 	conditions in Lake Champlain during the summer.

Comparability: The Vermont Department of Environmental Conservation Laboratory Quality Assurance Plan, including the standard operating procedures, is consistent with current EPA methods.  Lake stations are the same ones sampled since 1979 with the following ones being added since then: station 31 added in 1990; stations 32, 33, 34 and 35 added in 1992; station 36 added in 1994; station 37 added in 2003; and stations 38-42 added between 2008-2011.

Representativeness: Stations 1 – 42 were selected to represent the broad range of water quality conditions in the lake.  Stations 1, 25, 26, 27 and 28 have been officially dropped from the program.  Preliminary results from the Lake Champlain Diagnostic Feasibility Study indicated that these stations were not suitably located for long term water quality trend detection by the Lake Champlain Lay Monitoring Program.

Performance and System Audits

The LMP staff will inform monitors of any technique errors during quality assurance visits.  Staff will review with and demonstrate to monitors the proper technique when necessary.  Staff will read monitor comments on data sheets bi-weekly and monitor questions will be answered and assistance given when needed.  Monitors will be encouraged to call staff with any problems they have with any aspect of the program.

Performance and system audits for laboratory analytical centers are detailed in the Laboratory Quality Assurance Plan (VT DEC, 2013) and are the responsibility of the Laboratory Supervisor.

Element 8.	Training Requirements and Certification

The LMP Assistant is trained in all aspects of the program by the Project Manager.  Typically a new LMP Assistant will spend two weeks shadowing the Project Manager in the many aspects of the program.  Additionally, the LMP Assistant is given a copy of the Lay Monitoring Program Assistant Guide (Picotte, 2002) to read and to have on hand in the field.

All Lake Champlain Lay Monitors are trained in the sampling procedures at their lake station by the LMP staff and a list of trained monitors is maintained by the Project Manager.  During training all parts of the sampling procedure are explained in detail and demonstrated. The LMP staff and the monitor take turns performing each part of the sampling procedure.  Sections which present difficulties to the monitors are repeated several times until they are comfortable sampling on their own.  Monitors are given the data sheet to fill out and to use as a guide to the sampling steps.  All sampling steps are written on a laminated card and the monitors are reminded to refer to these steps when sampling.  Monitors are encouraged to take notes on procedures and follow along in the LMP Manual as well.  Trainings typically take two to four hours for monitors, depending on the location of their station.

Element 9.	Documentation and Records

Monitors are trained to use the program’s data sheets and equipment when sampling.  Data sheets and samples are properly stored until program staff picks them up once every two weeks (Vermont Department of Environmental Conservation, Lay Monitoring Program Manual, 2000).

Sample Custody Procedures

Samples will be collected from monitors by program staff and brought to the lab bi-weekly in labeled containers.  Program staff is responsible for logging the samples into the lab data management system where a unique identification number is assigned to each sample.  Program staff then deliver the sample containers to the appropriate storage area or analytical lab.  Individual analysts are responsible for retrieving samples from the storage areas for analysis.  Samples will not be used for enforcement purposes.  All data results are maintained in the VTDEC Watershed Management Division database management system.

Element 10. Sampling Process Design

Sampling Site Distribution

The current 23 monitoring stations are distributed throughout the lake (Table 2) and represent a broad range of water quality conditions.

Element 11. Sampling Methods Requirements

Sampling methods are covered in Element 6 of this QA/QC plan and described in the Vermont Department of Environmental Conservation, Lay Monitoring Program Manual (2000).

Table 4. Sampling Method and Quantity Requirements

| Location of Weekly Sampling | Sampling Method | Analysis Parameter | Sample Volume (ml) | Sample Container | Field Procedures |
| --- | --- | --- | --- | --- | --- |
| Lake Champlain Stations 4, 7, 10, 30 | Secchi Disk | Transparency | - | - | observation |
|  | Sub-Surface Grab (Station 30 only) | TP | 50 | Glass tube | none |
|  |  | Chlorophyll-a | 100 | Filter paper, (Glass Microfibre particular retention 1.6um) | filtration |
| Lake Champlain Stations 9, 11, 21, 22, 33, 38, 40, 41 | Secchi Disk | Transparency | - | - | observation |
|  | Hose Sample | TP | 50 | Glass tube | none |
|  |  | Chlorophyll-a | 100 | Filter paper (Glass Microfibre particular retention 1.6um) | filtration |

Element 12. Sample Handle and Custody Requirements

Reference – Element 9 of this QA/QC Plan.

Element 13. Analytical Methods Requirements

Sample Analysis

Table 5. Parameter Table

| Parameter | Number of Samplesa | Sample Matrix | DEC (SOP) Referenceb | EPA Analytical Method | Sample Preservation | Holding Time |
| --- | --- | --- | --- | --- | --- | --- |
| TP | 117 | water | 1.6 | 4500-P H c | none | 28 days |
| Chlorophyll-a | 234 | water | 5.4 | 445 Revision 1.2d | freeze, dark | 21 days |

a	Includes field QC samples from Program Staff.

b 	Vermont Department of Environmental Conservation Laboratory Quality Assurance Plan (2013), Appendix A –  Laboratory Standard Operating Procedures (March and June 2005 SOP)

c 	Standard Methods for the Examination of Water and Wastewater, 21st Edition (2005)

d	In Vitro Determination of Chlorophyll-a and Pheophytin-a in Marine and Freshwater Algae Fluorescence, 1997. National Exposure Research of Research and Development, USEPA.

Element 14. Quality Control Requirements

Laboratory Analytical Procedures

Reference – Sections 11 and 14 of Vermont Department of Environmental Conservation Laboratory Quality Assurance Plan (2013)

Field Samples

Lake Champlain has 42 lay monitoring stations (12 are currently being sampled through the LMP). They were selected to represent the broad range of water quality conditions in the lake.

Monitors are required to collect two different water samples, sample A and sample B from a separate sampling at their respected stations.

Collecting chlorophyll-a samples: The two samples (A and B) are filtered (100 mls each) and are assigned a unique laboratory identification number upon arrival at the lab.  The samples are analyzed as individual chlorophyll-a samples and two separate results are reported.

Collecting phosphorus samples: A 50 ml portion of sample B, stored in a glass test tube, is analyzed for total phosphorus.  Total phosphorus water samples are collected in duplicate at least one time during the summer (approximately 10% of all phosphorus samples).  Duplicate phosphorus samples are collected from a 50 ml portion of sample bottle A and a 50 ml portion from sample bottle B, with the sample from bottle A being labeled as the duplicate.  The phosphorus duplicates are collected by the monitors during the LMP staff field visits with the monitors.  During the annual LMP staff visits with the lay monitors, additional duplicate samples (minimum of 10 %) are taken for the laboratory staff to use as part of their quality assurance program, which includes a sample for analyzing spiked samples. The LMP staff will fill two 50 ml test tubes, one with lake water from sample bottle A to be used by the lab for spikes, and the other with lake water from sample bottle B, also for lab use.

RPD of Monitor Duplicate Samples:

RPD = (C1 - C2) x 100%

(C1 + C2)/2

RPD = relative percent difference

C1 = larger of the two observed values

C2 = smaller of the two observed values

Due to logistical constraints in picking up and delivering samples to the laboratory, it is not always possible to analyze all chl-a and TP samples within the prescribed 21- and 28-day hold times, although every effort will be made to do so.  These samples will be properly stored throughout this time.  A remark field in the database will be used to identify samples analyzed in the laboratory past their hold times so that appropriate data screening may be applied if deemed necessary at the time the data are statistically analyzed and reported.

Reference – Vermont Department of Environmental Conservation, Lay Monitoring Program Manual (2000)

Corrective Action

Upon joining the Lay Monitoring Program, all monitors are given a copy of the Vermont Lay Monitoring Program Manual, which contains explanations, graphics, and checklists for proper sampling techniques.  Monitors will be asked to review this manual and also be reminded that the sampling procedures are listed on a laminated card to be used while sampling in the field.  Monitors are required to follow the LMP sampling procedures to participate in the LMP program and are visited (checked) annually by program staff.

For laboratory use, corrective actions are defined in Section 15 of the Vermont Department of Environmental Conservation Laboratory Quality Assurance Plan (2013).

Element 15. Instrument/Equipment Testing, Inspection, and Maintenance Requirements

Laboratory Analysis QA/QC – Calibration Procedures, Analytical Procedures and Preventive Maintenance

Reference – Section 8, 9, and 13 of Vermont Department of Environmental Conservation Laboratory Quality Assurance Plan (2013)

Field Sampling Equipment

The Vermont DEC supplies all the equipment except for a boat and anchor to the volunteer monitors.  Before any equipment is supplied to a volunteer, it is carefully checked by LMP staff.  Secchi disk lines are measured and marked off in meters.  Hoses are also marked off in meter increments.  All Nalgene 500 ml sample bottles (each monitor is given a sample bottle “A” and “B”), hand filtering apparatuses, graduated cylinders, 5 gallon buckets, and hoses are acid washed (10% solution of sulfuric acid) and thoroughly rinsed before being given to monitors.  The 50 ml glass test tubes are disposable and provided clean and new from the DEC Laboratory.  All equipment is checked during the annual LMP staff field visits with monitors.  On a rotational basis, hoses are collected from the monitors and acid washed by LMP staff before being returned to monitors.  The monitors who plan to return to the program for the next season are asked to store the equipment during the winter months.  Monitors are given written directions on properly storing equipment during the winter months.  New filter papers, glass test tubes, and data sheets are provided at the start of each sampling season.

Reference – Vermont Lay Monitoring Program Manual, 2000

Element 16. Instrument Calibration and Frequency

Reference – Element 15 of this QA/QC Plan

Element 17. Inspection and Acceptance Requirements for Supplies

All monitoring supplies used are either the exact same make as equipment used in past years, or are comparable replacement products.  Most of the sampling equipment used is purchased through the laboratory supplier, VWR Scientific, to ensure consistent use of the exact same filter paper, sample bottles, graduated cylinders, and other field supplies needed.  The hoses and rope purchased are non-stretch.  Annual records of all equipment purchased and used by the LMP are kept to ensure consistency in selecting any new sampling equipment.

Reference – Element 15 of this QA/QC Plan and the Vermont Lay Monitoring Program Manual, 2000

Element 18. Data Acquisition Requirements

Monitors are provided with Watershed Management Division Vermont Lake Maps that show the locations of the sampling stations, along with GPS coordinates.  Monitors are trained by LMP staff to locate their sampling stations using these maps and, when possible, the GPS coordinates.

Element 19. Data Management

All sampling results are maintained in the VTDEC Watershed Management Division database management system.

Reference – Element 9 of this QA/QC Plan

Element 20. Assessments and Response Actions

Reference – Element 7 and Element 14 of this QA/QC Plan

Element 21. Reports

Data for each monitoring station will be summarized and compiled into an annual report for distribution to volunteer monitors, state agencies, and organizations and individuals interested in Lake Champlain's water quality.  This annual final report is the responsibility of Mark Mitchell, Project Manager.

Element 22. Data Review, Validation and Verification Requirements

Data Reduction

Reference – Section 10 of Vermont Department of Environmental Conservation Laboratory Quality Assurance Plan (2013)

Element 23. Validation and Verification Methods

The validation of laboratory data is the primary responsibility of the Lab Supervisor utilizing methods documented in Section 10 of the Vermont Department of Environmental Conservation Laboratory Quality Assurance Plan (2013).*

At the program level, the Project Manager validates the data according to the following process:

Secchi disk readings and total phosphorus concentrations from each lake are reviewed and compared to previous year’s data.  If any samples seem unusually high or low, then the monitor data sheets are checked for that day's sampling comments (monitors might be called as well) and the Laboratory Staff is consulted about possible errors.  All samples where monitors used questionable techniques, or where they noted problems with sampling or sample storage, and where chemists noted problems, are not validated and the data not used.

To average both the chlorophyll-a duplicates for a single concentration value, the two samples must be evaluated according to the following:

If H/L**<2.5, then both values are kept.

If H/L>2.5 lab and data sheets are checked for an explanation,

- if the lake is eutrophic or if algal blooms were present, both values are kept.

- if there is no written reason, then both values are tossed.

- if only one value is questionable, that value will be tossed and the other used.

*Reference – Vermont Department of Environmental Conservation Laboratory Quality Assurance Plan (2013), Section 9.

**H = high concentration, L = low concentration

Element 24.	Reconciliation with Data Quality Objectives

The LMP is a cooperative effort between the Vermont DEC and lake users to collect essential baseline water quality data on Vermont lakes. Monitors are asked to collect a minimum of nine samples during June, July and August – a minimum number of eight is needed to calculate summer means.  If fewer than eight samples are collected during the summer months, no annual mean can be calculated for that year and the data is used to describe only current water quality conditions, and not for long term trend analysis.  Monitors on more than 100 lakes in Vermont have participated in the LMP and have contributed substantially to the understanding of water quality conditions in Vermont lakes.

Reference – Element 14 of this QA/QC Plan

Reference – Vermont Lay Monitoring Program Manual, 2000

References

Standard Methods for the Examination of Water and Wastewater. 21st Edition. 2005 (EPA

Analytical Method, 4500-PF 445 Revision 1.2)

In Vitro Determination of Chlorophyll-a and Pheophytin-a in Marine and Freshwater Algae

Fluorescence, 1997. National Exposure Research of Research and Development, USEPA.

Environmental Protection Agency. 1996. The Volunteer Monitor’s Guide to Quality Assurance Project Plans

Vermont Department of Environmental Conservation Laboratory Quality Assurance Plan, 2013. Waterbury, VT

Vermont Department of Environmental Conservation, Vermont Lay Monitoring Program Manual, 2000. Waterbury, VT

Vermont Department of Environmental Conservation, Vermont Lay Monitoring Assistant Guide, 2002. Waterbury, VT

Appendix A. Lake Names and Locations

| LAKE/POND NAME | Latitude | Longitude | Total Depth of Station #1 (meters) |
| --- | --- | --- | --- |
| ADAMANT | 44.3313 | -72.50345 | 2 |
| ADAMS (WOODFORD) | 42.8869 | -73.0394 | 5 |
| AMHERST | 43.4861 | -72.7053 | 27 |
| ARROWHEAD MOUNTAIN | 44.66126 | -73.10833 | 7.6 |
| BEEBE (HUBARDTON) | 43.7344 | -73.1833 | 12 |
| BERLIN | 44.1839 | -72.5872 | 18 |
| BLISS | 44.3528 | -72.5025 | 4.5 |
| BOMOSEEN | 43.6494 | -73.2083 | 18.2 |
| BROWNINGTON | 44.8794 | -72.1478 | 9.2 |
| BUCK | 44.46248 | -72.39824 | 9.2 |
| BURR (SUDBURY) | 43.7656 | -73.1844 | 4.6 |
| CARMI | 44.97393 | -72.87549 | 11 |
| CASPIAN | 44.5866 | -72.31001 | 30 |
| CEDAR | 44.2506 | -73.1342 | 3.8 |
| CHIPMAN | 43.4089 | -73.0317 | 3.4 |
| CHITTENDEN | 43.72673 | -72.90371 | 14 |
| COLE | 43.1478 | -72.8056 | 3 |
| COLES | 44.5058 | -72.215 | 6.4 |
| CRYSTAL (BARTON) | 44.7328 | -72.1533 | 30.5 |
| CURTIS | 44.3881 | -72.4939 | 7.6 |
| DANBY | 43.3656 | -73.0522 | 2 |
| DERBY | 44.9556 | -72.0383 | 5.2 |
| DUNMORE | 43.9122 | -73.0764 | 30 |
| EAST LONG | 44.4475 | -72.3525 | 30 |
| ECHO (CHARLESTON) | 44.86 | -71.9928 | 39 |
| ECHO (HUBARDTON) | 43.7475 | -73.1828 | 12.2 |
| ECHO (PLYMOUTH) | 43.4775 | -72.7014 | 28 |
| EDEN | 44.7228 | -72.5014 | 11.9 |
| ELFIN | 43.4694 | -72.9881 | 11 |
| ELLIGO | 44.59381 | -72.3556 | 30.3 |
| ELMORE | 44.5347 | -72.5256 | 5.2 |
| EMERALD | 43.2742 | -73.0069 | 12 |
| FAIRFIELD | 44.8453 | -72.9967 | 13 |
| FAIRLEE | 43.8847 | -72.2408 | 15 |
| FERN | 43.8628 | -73.0706 | 12.7 |
| FOSTERS | 44.32873 | -72.21048 | 4 |
| GILLETT | 44.3525 | -72.9661 | 2 |
| GLEN | 43.6664 | -73.2417 | 18.3 |
| GREAT HOSMER | 44.6858 | -72.3644 | 13 |
| GREEN RIVER RESERVOIR | 44.6544 | -72.5231 | 28 |
| GREENWOOD | 44.4578 | -72.4258 | 9 |
| GROTON | 44.2789 | -72.2672 | 13 |
| HALLS | 44.0861 | -72.1239 | 9 |
| HARVEYS | 44.2939 | -72.1375 | 40 |
| HIGH (SUDBURY) | 43.75332 | -73.15336 | 17 |
| HOLLAND | 44.98588 | -71.92928 | 11.5 |
| HORTONIA | 43.7553 | -73.2022 | 18 |
| INDIAN BROOK RESERVOIR | 44.5328 | -73.0972 | 7.6 |
| IROQUOIS | 44.3658 | -73.0833 | 10 |
| ISLAND | 44.8075 | -71.8733 | 12 |
| JOES (DANVILLE) | 44.4081 | -72.2208 | 15 |
| LITTLE (WELLS) | 43.43384 | -73.20497 | 2 |
| LONG (WESTMORE) | 44.7517 | -72.0175 | 23 |
| LOWELL | 43.2272 | -72.7642 | 7.3 |
| LYFORD | 44.4397 | -72.2511 | 6.1 |
| MAIDSTONE | 44.6522 | -71.6469 | 30 |
| MARTINS | 44.3083 | -72.2167 | 5.5 |
| MEMPHREMAGOG | 44.9628 | -72.2228 | 8.3 |
| MEMPHREMAGOG - SOUTH BAY | 44.9203 | -72.2097 | 5 |
| MILES | 44.4472 | -71.8139 | 16.7 |
| MIRROR | 44.3961 | -72.4439 | 32 |
| MOLLEYS FALLS | 44.3625 | -72.2961 | 11 |
| MOREY | 43.9247 | -72.1533 | 11 |
| MUCKROSS/GOULDS | 43.276 | -72.45808 | 3 |
| NELSON/FOREST (CALAIS) | 44.4075 | -72.4389 | 29 |
| NEWARK | 44.7175 | -71.9822 | 9 |
| NICHOLS | 44.4567 | -72.3383 | 24 |
| NINEVAH | 43.4689 | -72.7533 | 3.5 |
| NORTH MONTPELIER | 44.3047 | -72.4478 | 3.6 |
| NORTON (Station 2) | 44.9403 | -71.8619 | 9.1 |
| PARAN | 42.9328 | -73.2353 | 7 |
| PARKER | 44.71926 | -72.23425 | 12 |
| PEACHAM | 44.3306 | -72.26 | 15 |
| PENSIONER | 44.8783 | -72.0567 | 12 |
| PERCH (BENSON) | 43.7503 | -73.2808 | 9.1 |
| PINNEO | 43.6517 | -72.4314 | 3 |
| RAPONDA | 42.8733 | -72.82 | 4.8 |
| RESCUE | 43.4494 | -72.7008 | 27 |
| RICKER | 44.2456 | -72.2436 | 9 |
| RUNNEMEDE | 43.48467 | -72.38874 | 2.9 |
| SABIN/WOODBURY | 44.4031 | -72.4186 | 5.2 |
| SALEM | 44.93 | -72.1044 | 18 |
| SEYMOUR | 44.8856 | -71.9797 | 48 |
| SHADOW (GLOVER) | 44.6675 | -72.2258 | 42.4 |
| SHELBURNE | 44.3922 | -73.1608 | 7.6 |
| SILVER (BARNARD) | 43.7289 | -72.6089 | 9.5 |
| SOUTH (EDEN) | 44.6833 | -72.5275 | 20 |
| SOUTH (MARLBORO) | 42.9178 | -72.6833 | 11 |
| SPRING (SHREWSBURY) | 4330 | 7255 | 26 |
| ST. CATHERINE | 43.4758 | -73.2153 | 20 |
| STAR | 43.4169 | -72.8183 | 2 |
| STRATTON | 43.1047 | -72.9694 | 5 |
| SUNRISE | 43.7606 | -73.2611 | 13 |
| SUNSET (BENSON) | 43.75516 | -73.27256 | 32 |
| SUNSET (MARLBORO) | 42.9178 | -72.6833 | 11 |
| SUNSET (BROOKFIELD) | 44.0436 | -72.6039 | 8.5 |
| TICKLENAKED | 44.19067 | -72.0989 | 15.4 |
| VALLEY | 44.4478 | -72.4407 | 21 |
| WAPANACKI | 44.55868 | -72.39961 | 2 |
| WATERBURY | 44.3858 | -72.7636 | 30 |
| WILLOUGHBY | 44.7517 | -72.0622 | 94 |
| WINONA | 44.1747 | -73.0897 | 2 |
| WOODFORD/BIG | 42.89072 | -73.06953 | 7.6 |
| WOODWARD | 43.565 | -72.7597 | 14 |

Note: Highlighted stations were sampled through the LMP in 2017 and/or are expected to be sampled in 2018. (http://dec.vermont.gov/watershed/lakes-ponds/monitor/lay-monitoring)